## 01_Exec Summary
Project East Grant - Stage 3-4 Stakeholder Engagement Plan
Executive Topic | Summary
Plan Focus | Data validation, environmental inputs, infrastructure/dry and wet utility constraints, land/legal closure, and stakeholder action close-out.
Highest Priority Stakeholders | RCRC, Riyadh Plan Team, Ministry of Energy/SEC/Aramco, Riyadh Municipality, MEWA(NWC; SWA), Authority, MOMAH, SPGA/MOJ.
Main Delivery Risks | Delayed data, conflicting spatial data, pipeline constraints buffer, ownership/title deed gaps, and late Stakeholder reply.
Immediate Management Action | Confirm focal points, update open MoM action status, and schedule first-wave for this stage meetings within two weeks.
Exec Summary | Formula / Result
Total Strategy Stakeholders | 15
Critical Priority Stakeholders | 10
Critical Stakeholders Meeting | 4
Previous meetings | 14
Open Previous Actions | 30
Critical Risks | 3
Unanswered questions | 82

## 02_Engagement Strategy
Stakeholder Engagement Strategy
This sheet defines who to engage, why, what is required, how often to engage,
Priority Rank | Stakeholder / Cluster | Specific Department / Counterpart | Technical specialization | Stage 3–4 Engagement Purpose | Influence | Interest | Priority | Engagement Objective | Information / Decision Required | Recommended Channel | Project Owner | Frequency | Planned Contact Window | Expected Output | Escalation Route | Current Status | Source / Evidence
1 | RCRC | Planning Advisor; Urban Programs & Land Use; Mobility; Infrastructure & Utilities; Sustainability; Legal; GIS | Client / Approval Authority | Confirm Stage 4 direction, priority stakeholder sequence, key decisions, and escalation route for unresolved Stage 2–3 items. | High | High | Critical | Confirm Stage 4 structure plan direction, unresolved Stage 2-3 action closure, and approval route | Decision on preferred direction, stakeholder sequence, and issue escalation ownership | Weekly progress meeting + technical gates | WSP PM / Stakeholder Lead | Weekly | Immediate and throughout Stage 4 | RCRC-endorsed engagement route and decision log | WSP PM -> RCRC PM -> RCRC leadership | In Progress | SEMP; Riyadh Plan MoM; Stage 3 workshop
2 | Riyadh Plan Team | RCRC / Riyadh Plan alignment team | Strategic Planning | Validate the Structure Plan direction against Riyadh Plan, including site role, centres hierarchy, transport logic, and key city-wide constraints. | High | High | Critical | Validate the Stage 4 structure plan against Riyadh Plan direction | Confirmation of site role, hierarchy of centres, transport logic and any constraints before finalizing structure plan | Focused alignment workshop | Urban Planning Lead | At Stage 4 gates | Before draft structure plan freeze | Written alignment record and direction to incorporate | RCRC Planning -> RCRC leadership | Planned | Riyadh Plan Alignment MoM, 17-Feb-2026
3 | Ministry of Energy / SEC / National Grid / Saudi Aramco | MoE energy planning; SEC/NG power; Aramco pipeline / Committee No. 85 | Dry Utilities / Strategic Infrastructure | Review energy and pipeline assumptions, confirm buffers and exclusion zones, and provide feedback on power demand, cost estimates, and Committee No. 85 coordination. | High | High | Critical | Share Stage 4 structure plan assumptions and obtain technical feedback on energy infrastructure | Pipeline-affected land GIS, buffers, power demand inputs, cost-estimate review, Committee No. 85 coordination | Arabic technical workshop + Excel question tracker | Dry Utilities Lead | Every 3 weeks / key gates | Early Stage 4 and before cost inputs | Confirmed energy constraints and dry utility follow-up list | RCRC PM -> MoE focal point -> Committee No.85 | In Progress | MoE MoM 11-May-2026; MoE 2nd MoM 07-Jul-2026
4 | Riyadh Municipality | Planning & Lands Departments | Municipal / Planning & Lands | align on grants, and title lands context. | High | High | Critical | Obtain and validate data required for Stage 4 hydrology model and flood buffers | HEC-HMS/RAS files, reports, culvert data, spot levels, coordinate system confirmation | Technical data workshop + formal RFI | Hydrology Lead | Bi-weekly until data closed | Immediate | Validated the data | RCRC PM -> Amanah Stormwater Director | Open - verify status | Stormwater MoM 18-Jun-2026
5 | MEWA | Environment, Water, Agriculture; irrigation and environmental approvals as applicable | Environment / Water | Confirm environmental, water, irrigation, groundwater, and approval requirements affecting the Structure Plan and EIA. | High | Medium | High | Confirm environmental and water constraints affecting Stage 4 structure plan and EIA | Environmental datasets, water resource constraints, irrigation networks, environmental approval requirements | Technical workshop + formal correspondence | Environment Lead | Two Stage 4 checkpoints | Early Stage 4 | EIA input register and environmental constraints map | RCRC -> MEWA nominated focal point | Planned | SEMP stakeholder register; Baseline environment scope
6 | Imam Abdulaziz bin Mohammed Royal Reserve Authority | Reserve planning, ecology, biodiversity, environmental integration | Environment / Royal Reserve | Validate ecological corridors, reserve interface, environmental continuity, watershed , and required buffers . | High | High | High | Validate ecological corridors and reserve interface before Stage 4 plan finalisation | Reserve boundary/buffer inputs, watershed implications, ecological constraints and queries response | Focused environmental workshop | Environment Lead | One primary workshop + follow-up | After draft environmental/wadi layers | Agreed reserve interface principles | RCRC -> Reserve Authority focal point | Open - verify status | Royal Reserve MoM 04-May-2026
7 | Riyadh Infrastructure Projects Centre (RIPC) | Infrastructure coordination and service provider strategy | Infrastructure / Delivery | Align infrastructure phasing, service provider coordination, funding mechanism, and delivery assumptions. | High | Medium | High | Align Stage 4 infrastructure phasing with service provider strategies | Masterplan strategy, KMZ verification, funding mechanism, service provider coverage | Technical coordination workshop | Infrastructure Lead | At infrastructure phasing gates | Early to mid Stage 4 | Infrastructure coordination plan and funding model inputs | RCRC PM -> RIPC focal point | Open - verify status | RIPC MoM 12-May-2026
8 | MOMAH | Urban planning; housing; land use regulation | National Planning / Housing | priority stakeholder sequence, key decisions, and escalation route for unresolved Stage 2–3 items. | High | High | Critical | Validate Stage 4 land-use assumptions and housing-related implications | Ministry future plans, Plot No.2 confirmation, approved plan integration, compensation comments | Formal alignment meeting | Urban Planning Lead | Stage 4 land use checkpoints | Before structure plan issue | MOMAH comments register and action closure | RCRC -> MOMAH focal point | Open - verify status | MOMAH MoM 14-May-2026
9 | Ministry of Industry and Mineral Resources | Mineral resources / industrial constraints | Industry / Resources | Confirm silica/sand reserve boundaries, industrial or mineral constraints, exclusion zones for developable land. | High | Medium | High | Clarify mineral/industrial constraints and implications on land-use options | Reserve boundaries, exclusion zones, policy positions, GIS data, future plans | Targeted technical meeting | Urban Planning / Environment Lead | One meeting + data follow-up | Urgent Stage 4 | MIMR constraint register and GIS layer request | RCRC -> Ministry focal point | Not Started | SEMP; RIPC MoM references silica reserves
10 | Ministry of Transport & Logistics / RGA / TGA / SAR | Roads, transport, logistics, rail and mobility interfaces | Transport / Logistics | Validate road, logistics, rail, public transport, ROW, and corridor assumptions affecting access and the Structure Plan. | High | Medium | High | Confirm road/transport assumptions affecting the structure plan | Planned road corridors, ROW, public transport, rail/logistics interfaces, mobility standards | Transport technical workshop | Transport Lead | Two checkpoints | Before movement network freeze | Transport assumptions log and network alignment comments | RCRC Mobility -> MOTLS/RGA/SAR focal points | Planned | SEMP stakeholder register; Baseline transport scope
11 | SPGA | State-owned properties and land management | Land Ownership | Confirm state-owned land, land availability, affected parcels, and ownership constraints before. | High | Medium | High | Close land ownership gaps before land consolidation and parcel reassignment decisions | Ownership confirmation, land availability, state property constraints | Formal correspondence + legal/land workshop | Land / Legal Lead | Weekly until major gaps closed | Immediate | Updated land ownership register | RCRC Legal/Lands -> SPGA | Open - verify status | SEMP; baseline land/ownership scope
12 | Ministry of Justice | Title deeds, legal ownership verification | Legal / Governance | Confirm title deed data, legal ownership status, Stage 4 parcel decisions. | High | Medium | High | Confirm title deed and legal ownership data affecting Stage 4 parcel decisions | Title deed data, legal status, disputed cases, ownership methodology | Formal data request + legal workshop | Legal Lead | Weekly until data closed | Immediate | Legal ownership validation log | RCRC Legal -> MOJ focal point | Open - verify status | SEMP; MOMAH/Wadi MoMs
13 | Utilities Cluster - Wet Utilities | NWC; SWA; SIO; RIPC where relevant | Wet Utilities | Validate potable water, sewage, TSE, irrigation network capacity, standards, cost assumptions, and phasing constraints. | Medium | High | High | Validate wet utility demand assumptions and servicing strategy | Network capacity, standards, cost unit rates, phasing constraints | Joint technical workshop | Wet Utilities Lead | At utility demand gates | Mid Stage 4 | Wet utility assumptions and data gaps log | RCRC Infrastructure -> utility focal points | Planned | SEMP; Baseline utilities scope
14 | Ministry of Defense /Ministry of Interior | Defense land / restricted areas | Restricted Lands | Confirm restricted land boundaries, no-development areas, and no-relocation assumptions affecting the Structure Plan. | High | Low | Medium | Validate defense land boundary and no-development assumptions | MOD land boundary and restrictions | Formal coordination through RCRC | Legal / GIS Lead | As required | Before developable land freeze | Validated no-go layer | RCRC leadership channels | Planned | Riyadh Plan MoM
15 | Biotic | Economy and Technology | Economy and Technology |  | low | low | [5 empty] | once if needed

## 03_Schedule (hidden)
Proposed dates are sequenced from internal alignment to external technical validation and should be confirmed with RCRC/Lubna.
No. | Stakeholder / Cluster | Meeting Type | Proposed Date | Timing Gate | Objective | Inputs Required Before Meeting | Expected Outputs | Preparation Owner | Follow-up Owner | Status | Action Closure Deadline | Assumption / Dependency
1 | external RCRC | Internal technical gate | 2026-07-14 | Before external Stage 4 outreach | Agree stakeholder sequence, agenda packs and decision route | Stage 3 outputs, preferred direction, open MoM tracker | Approved engagement route and priority list | WSP PM | Stakeholder Lead | Planned | 2026-07-16 | Assumes RCRC availability after Stage 3 VP/SC direction
2 | Riyadh Plan Team | Strategic alignment workshop | 2026-07-16 | Before draft structure plan freeze | Confirm city-wide alignment for Stage 4 structure plan | Preferred strategy, centres/mobility assumptions, maps | Confirmed alignment comments | Urban Planning Lead | Stakeholder Lead | Planned | 2026-07-21 | Dependent on internal RCRC gate
3 | Ministry of Energy / SEC / National Grid / Aramco | Dry utilities / pipeline workshop | 2026-07-20 | Early Stage 4 | Validate pipeline, power and cost review requirements | Stage 3 structure outputs, GIS layers, demand assumptions | Energy constraints log and cost-review route | Dry Utilities Lead | Dry Utilities Lead | Planned | 2026-07-27 | Committee No. 85 representatives to be included
4 | Riyadh Municipality - Stormwater + land Granted | Joint hydrology / wadi workshop | 2026-07-22 | Before land-use freeze | Close hydrology data gaps and agree wadi buffer approach | Draft wadi layers, old study review, action tracker | Hydrology data decision log and buffer principles | Hydrology Lead | Hydrology Lead | Planned | 2026-07-29 | Requires available Amanah data or clear data limitations
5 | MEWA / SIO / Environmental Centers | Environmental and water constraints workshop | 2026-07-26 | Before EIA scoping freeze | Confirm environmental and water constraints for Stage 4 | Environment baseline, wadi layers, protected areas map | EIA input register | Environment Lead | Environment Lead | Planned | 2026-08-02 | MEWA focal point to be nominated
6 | Royal Reserve Authority | Reserve interface workshop | 2026-07-28 | After wadi/environment layers | Validate ecological corridors and reserve interface | Draft ecological corridors, hydrology implications, queries tracker | Reserve interface principles | Environment Lead | Stakeholder Lead | Planned | 2026-08-04 | Linked to prior Royal Reserve action tracker
7 | MOMAH | Planning and housing alignment | 2026-07-30 | Before structure plan issue | Confirm land-use and housing policy alignment | Draft land-use plan, approved plan integration note | MOMAH feedback log | Urban Planning Lead | Urban Planning Lead | Planned | 2026-08-06 | Plot No. 2 and future plans to be clarified
8 | RIPC | Infrastructure phasing / delivery workshop | 2026-08-03 | Before infrastructure phasing freeze | Align service provider strategy and funding model inputs | KMZ, draft phasing, utility assumptions | Infrastructure phasing inputs | Infrastructure Lead | Infrastructure Lead | Planned | 2026-08-10 | Depends on KMZ and service provider strategy availability
9 | Ministry of Industry and Mineral Resources | Mineral / industrial constraints meeting | 2026-08-05 | Before developable land freeze | Confirm mineral/industrial constraints including silica/sand reserves | Draft constraints map, reserve boundary query, GIS request | MIMR constraint confirmation / data request | Urban Planning Lead | Environment Lead | Planned | 2026-08-12 | High priority due recent client request
10 | MOTLS / RGA / TGA / SAR | Transport network workshop | 2026-08-09 | Before movement network freeze | Validate transport corridors, ROW and logistics interfaces | Draft movement plan, Riyadh Plan transport assumptions | Network alignment comments | Transport Lead | Transport Lead | Planned | 2026-08-16 | Dependent on Riyadh Plan alignment
11 | SPGA + MOJ | Land and legal data closure workshop | 2026-08-11 | Before parcel reassignment methodology | Close ownership/title deed gaps and legal action items | Parcel register, title deed gaps, affected land maps | Validated legal/ownership gaps log | Legal/Land Lead | Legal/Land Lead | Planned | 2026-08-18 | May need separate meetings if decision-makers differ
PEG Stage 3 - 4Stakeholder Coordination plan
Prepared for Lubna/Hind ¦ Use this sheet to coordinate meeting requests, client review windows, and sequencing for Stage 3 stakeholder engagement.
Note: preparing ppt for each stakeholder take 2 working days and then send it to the client before the meeting to reivew , 1 working day for client review, then finalize and hold the meeting.( total 4 days)
Total meetings in tracker |  |  |  |  | Primary Stage 3 meetings | [7 empty] | Meetings completed In the past stages
8 |  |  |  |  | 3 | [7 empty] | 12
Seq | Priority | Track | Stakeholder | Recommended Department / Team | Responsibility Snapshot | Stage 3 -4 Meeting Objective | Key Output | Proposed Week | Meeting Date | Draft to Client | Final Deck | MOM Due | Lubna/Hind Request | Status | Owner | Notes / Dependencies
1 | High | Supporting Coordination | Riyadh Amanah | Urban Planning | Local planning authority for development history, zoning evolution, grants and title context | Clarify site development history, key planning updates, and the status of the 12,000 granted parcels, including the 5,000 unallocated parcels. | Planning history note and zoning clarifications | Week1 | 2026-07-14 | 2026-07-12 | 2026-07-13 | 2026-07-15 | Not sent | Draft | Molham (WSP) | High-value meeting; prepare maps and targeted questions
6 | High | Parallel Follow-up | Ministry of Municipalities (Momah) | Urban Planning | Define planning rules, land uses, and development requirements. | Align on planning requirements and approvals.Confirm allocation records and identify the required pathway for unresolved parcels | MOMAH feedback and planning guidance. | Week 1 | 2026-07-14 | 2026-07-12 | 2026-07-13 | 2026-07-15 | Not sent | Not started | Molham (WSP) | Confirm planning approvals and land-use requirements.
2 | High | Supporting Coordination | Ministry of Energy | Energy policy / coordination counterpart | Government counterpart for strategic energy assumptions and alignment across the energy ecosystem | Confirm any strategic assumptions relevant to Project Eat Grant utilities planning and costing | Energy policy assumptions log | Week 2 | 2026-07-20 | 2026-07-16 | 2026-07-17 | 2026-07-21 | Not sent | Not started | Molham (WSP) | Keep focused on assumptions rather than detailed network design
3 | Medium | Supporting Coordination | Saudi Energy (SE) | Network / distribution counterpart | Primary electricity service and distribution counterpart for supply assumptions and network planning | Confirm latest electricity standards, available data and cost assumptions | Validated SEC assumptions and inputs | Week 2 | 2026-07-20 | 2026-07-16 | 2026-07-17 | 2026-07-21 | Not sent | Not started | Molham (WSP) | Coordinate with Ministry of Energy if strategic assumptions are needed
4 | Medium | Supporting Coordination | Saudi Aramco | Pipelines & Assets | Pipelines, corridors, and technical approvals | Confirm anyReview pipeline constraints and protection requirements strategic assumptions relevant to Project Eat Grant utilities planning and costing | Pipeline constraints and approval requirements | Week2 | 2026-07-20 | 2026-07-16 | 2026-07-17 | 2026-07-21 | Not sent | Not started | Molham (WSP) | Priority meeting; key source for parcel and planning data.
5 | Medium | Supporting Coordination | Saudi Electricity Regulatory Authority (SERA) | Regulation & Standards | Electricity regulations and service standards | Align on regulatory requirements and service standards | Regulatory guidance and compliance requirements | Week 2 | 2026-07-20 | 2026-07-16 | 2026-07-17 | 2026-07-21 | Not sent | Not started | Molham (WSP) | Validate regulatory and compliance requirements.
7 | Medium | Supporting Coordination | MEWA | Water / Environment counterpart | National counterpart for water, environment and agriculture matters affecting hydrology, irrigation and environmental baselines | Confirm latest technical data, assumptions and standards affecting Project Eat Grant | Validated MEWA assumptions and data needs | Week2 | 2026-07-21 | 2026-07-19 | 2026-07-20 | 2026-07-22 | Not sent | Not started | Molham (WSP) | Coordinate with utilities cluster deck
8 | Medium | Supporting Coordination | National Water Company (NWC) | Water and wastewater services counterpart | Operating counterpart for water supply, wastewater and service delivery assumptions | Confirm latest water / wastewater data, standards and cost assumptions | Validated NWC assumptions and inputs | Week 2 | 2026-07-21 | 2026-07-19 | 2026-07-20 | 2026-07-22 | Not sent | Not started | Molham (WSP) | Useful before Stage 4 utilities consolidation
9 | Medium | Supporting Coordination | Saudi Water Authority (SWA) | Water Strategy & Policy | Water policies, resources, and infrastructure planning | Align on strategic water planning assumptions | Water policy and infrastructure guidance | Week 2 | 2026-07-21 | 2026-07-19 | 2026-07-20 | 2026-07-22 | Not sent | Not started | Molham (WSP) | Useful before Stage 4 utilities consolidation
10 | Medium | Supporting Coordination | Saudi Irrigation Organization (SIO) | Irrigation Planning | Irrigation systems and water efficiency | Review irrigation opportunities and water reuse potential | Irrigation and water reuse recommendations | Week 2 | 2026-07-21 | 2026-07-19 | 2026-07-20 | 2026-07-22 | Not sent | Not started | Molham (WSP) | Review irrigation and water reuse opportunities.
Formulas:
Action Closure Deadline = IF(ISBLANK([Follow-up Owner]),"",WORKDAY([Follow-up Owner],-1))
Assumption / Dependency = IF(ISBLANK([Follow-up Owner]),"",WORKDAY([Follow-up Owner],1))
Note on A20: Total meetings in tracker
Note on F20: Primary Stage 3 meetings
Note on N20: Meetings completed
Note on J23: User input: enter the confirmed meeting date. All working dates on the right update automatically.
Note on N23: Track whether Lubna has formally requested / confirmed the meeting.
Note on O23: Use the dropdown to track the live status of each meeting.

## 04_Meeting Agendasxxxxxxxxxxxxx (hidden)
Stakeholder-Specific Meeting Agendas
Each agenda is linked to Project East Grant Stage 4 decisions and avoids generic discussion topics.
Meeting ID | Stakeholder / Cluster | Meeting Objective | Project-Specific Background | Agenda Item | Discussion Focus / Questions | Required Input or Decision | Duration (min) | Lead | Expected Output
M01 | RCRC Stage 4 Gate | Confirm the Stage 4 engagement route and technical decision process. | Stage 4 will translate Stage 3 direction into structure plan, master plan, EIA and hydrology outputs. | Stage 3 decision recap | Confirm preferred direction and open issues from Stage 3 | Approved assumptions to carry into Stage 4 | 10 | WSP PM | Confirmed decision baseline
M01 | RCRC Stage 4 Gate | Confirm the Stage 4 engagement route and technical decision process. | Stage 4 will translate Stage 3 direction into structure plan, master plan, EIA and hydrology outputs. | Stakeholder priority review | Agree which stakeholders require early Stage 4 meetings | Confirmed priority list and sequencing | 15 | Stakeholder Lead | Updated schedule
M01 | RCRC Stage 4 Gate | Confirm the Stage 4 engagement route and technical decision process. | Stage 4 will translate Stage 3 direction into structure plan, master plan, EIA and hydrology outputs. | Open actions review | Review outstanding MoM actions from Stage 2-3 | Action owner and due date confirmation | 20 | Stakeholder Lead | Action tracker baseline
M01 | RCRC Stage 4 Gate | Confirm the Stage 4 engagement route and technical decision process. | Stage 4 will translate Stage 3 direction into structure plan, master plan, EIA and hydrology outputs. | Escalation route | Confirm how delayed data or conflicting positions will be escalated | Escalation route and response timing | 15 | WSP PM | Escalation protocol
M01 | RCRC Stage 4 Gate | Confirm the Stage 4 engagement route and technical decision process. | Stage 4 will translate Stage 3 direction into structure plan, master plan, EIA and hydrology outputs. | Next steps | Confirm outgoing meeting requests and deck preparation responsibilities | Approval to proceed | 10 | WSP PM | Mobilization actions
M02 | Riyadh Plan Team | Validate Stage 4 structure plan direction against Riyadh Plan logic. | Riyadh Plan alignment previously emphasized city role, centres hierarchy, transport logic and 20-50 year ambition. | Site role within Riyadh | Does the Stage 4 structure plan support the intended role of the Grant/Ruma area? | Confirmation of site role and mission | 15 | Urban Planning Lead | City-role decision note
M02 | Riyadh Plan Team | Validate Stage 4 structure plan direction against Riyadh Plan logic. | Riyadh Plan alignment previously emphasized city role, centres hierarchy, transport logic and 20-50 year ambition. | Centres and employment logic | Confirm centre hierarchy, population and employment assumptions | RP alignment comments | 20 | Urban Planning Lead | Centres hierarchy inputs
M02 | Riyadh Plan Team | Validate Stage 4 structure plan direction against Riyadh Plan logic. | Riyadh Plan alignment previously emphasized city role, centres hierarchy, transport logic and 20-50 year ambition. | Transport framework | Review transport corridors and network hierarchy against RP inputs | Transport assumptions endorsed or corrected | 20 | Transport Lead | Network alignment comments
M02 | Riyadh Plan Team | Validate Stage 4 structure plan direction against Riyadh Plan logic. | Riyadh Plan alignment previously emphasized city role, centres hierarchy, transport logic and 20-50 year ambition. | No-go and restricted lands | Confirm mapping of MOD, MOI, reserves, buffers and no-go zones | Validated constraints map | 15 | GIS Lead | Updated GIS action list
M02 | Riyadh Plan Team | Validate Stage 4 structure plan direction against Riyadh Plan logic. | Riyadh Plan alignment previously emphasized city role, centres hierarchy, transport logic and 20-50 year ambition. | Action closure | Agree follow-up information and timing | Agreed actions | 10 | Stakeholder Lead | MoM + action tracker
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Stage 4 structure plan overview | Present structure plan assumptions, phasing and affected lands | Confirmation of review scope | 10 | Dry Utilities Lead | Meeting scope agreed
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Pipeline corridors and buffers | Confirm pipeline alignment, affected title deeds and restricted uses | Pipeline-affected GIS requirements | 20 | Dry Utilities Lead | Pipeline constraint log
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Power demand and grid planning | Review demand assumptions, substations, grid reinforcement and overhead line constraints | Demand information required / feedback route | 20 | Electrical Lead | Power demand action list
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Infrastructure cost estimate process | Agree how MoE/SEC will review preliminary cost estimates | Cost review protocol | 15 | Cost / Utilities Lead | Cost review pathway
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Committee No.85 coordination | Confirm participation of RCRC Committee No.85 representatives | Named participants and cadence | 10 | RCRC / WSP PM | Coordination route
M03 | Ministry of Energy / SEC / National Grid / Aramco | Validate Stage 4 energy, pipeline and dry utility constraints. | Previous MoE meetings identified pipeline protection, Committee No.85 coordination, cost estimate review and power demand requirements. | Next steps | Agree three-week cadence and submission package | Submission package checklist | 5 | Stakeholder Lead | MoM + actions
M04 | Riyadh Municipality - Stormwater + Wadi Al-Sulai | Close hydrology data gaps and validate wadi buffer approach for Stage 4. | Previous meetings confirmed old Amanah hydrology data is not sufficient for final decisions and wadi buffers are case-by-case. | Hydrology baseline status | Present current modelling assumptions and limitations | Agreement on data limitations | 15 | Hydrology Lead | Baseline limitation note
M04 | Riyadh Municipality - Stormwater + Wadi Al-Sulai | Close hydrology data gaps and validate wadi buffer approach for Stage 4. | Previous meetings confirmed old Amanah hydrology data is not sufficient for final decisions and wadi buffers are case-by-case. | HEC-HMS/RAS and survey data | Confirm availability, coordinate system and delivery route | Data handover or confirmation of non-availability | 20 | Hydrology Lead | Data register update
M04 | Riyadh Municipality - Stormwater + Wadi Al-Sulai | Close hydrology data gaps and validate wadi buffer approach for Stage 4. | Previous meetings confirmed old Amanah hydrology data is not sufficient for final decisions and wadi buffers are case-by-case. | Wadi buffer principles | Review dynamic buffer approach based on hydrology, landscape and ecology | Buffer principles for Stage 4 | 20 | Urban Design / Hydrology Lead | Buffer decision note
M04 | Riyadh Municipality - Stormwater + Wadi Al-Sulai | Close hydrology data gaps and validate wadi buffer approach for Stage 4. | Previous meetings confirmed old Amanah hydrology data is not sufficient for final decisions and wadi buffers are case-by-case. | Affected parcels and governance | Discuss impacts on approved/unapproved subdivisions and compensation interface | Land treatment inputs | 15 | Land / Legal Lead | Parcel impact actions
M04 | Riyadh Municipality - Stormwater + Wadi Al-Sulai | Close hydrology data gaps and validate wadi buffer approach for Stage 4. | Previous meetings confirmed old Amanah hydrology data is not sufficient for final decisions and wadi buffers are case-by-case. | Next steps | Agree data validation and model update timeline | Closed action tracker | 10 | Stakeholder Lead | MoM + action list
M05 | MEWA / SIO / Environmental Centers | Confirm environmental and water constraints needed for Stage 4 EIA and structure plan. | Stage 4 includes environmental impact and hydrology outputs; MEWA/SIO inputs are needed for environmental and water constraints. | Project and Stage 4 scope | Present structure plan, EIA and hydrology tasks | MEWA review scope confirmed | 10 | Environment Lead | Scope alignment
M05 | MEWA / SIO / Environmental Centers | Confirm environmental and water constraints needed for Stage 4 EIA and structure plan. | Stage 4 includes environmental impact and hydrology outputs; MEWA/SIO inputs are needed for environmental and water constraints. | Environmental constraints | Confirm any protected habitats, vegetation, sensitive areas or environmental requirements | Environmental input register | 20 | Environment Lead | Constraints list
M05 | MEWA / SIO / Environmental Centers | Confirm environmental and water constraints needed for Stage 4 EIA and structure plan. | Stage 4 includes environmental impact and hydrology outputs; MEWA/SIO inputs are needed for environmental and water constraints. | Water and irrigation interfaces | Discuss groundwater, irrigation networks, water resource constraints and reuse opportunities | Water-related requirements | 20 | Wet Utilities Lead | Water action list
M05 | MEWA / SIO / Environmental Centers | Confirm environmental and water constraints needed for Stage 4 EIA and structure plan. | Stage 4 includes environmental impact and hydrology outputs; MEWA/SIO inputs are needed for environmental and water constraints. | Approval and permitting route | Clarify any NCEC/MEWA requirements for EIA or future development | Approval process note | 15 | Environment Lead | Permitting pathway
M05 | MEWA / SIO / Environmental Centers | Confirm environmental and water constraints needed for Stage 4 EIA and structure plan. | Stage 4 includes environmental impact and hydrology outputs; MEWA/SIO inputs are needed for environmental and water constraints. | Data requests | Agree datasets and response dates | Formal RFI list | 10 | Stakeholder Lead | RFI tracker
M06 | Royal Reserve Authority | Validate reserve interface, ecological corridors and watershed implications. | The previous meeting highlighted ecological continuity, watershed implications and the need for collaborative technical validation. | Recap of previous actions | Confirm status of Excel queries and data received | Action closure status | 10 | Stakeholder Lead | Updated tracker
M06 | Royal Reserve Authority | Validate reserve interface, ecological corridors and watershed implications. | The previous meeting highlighted ecological continuity, watershed implications and the need for collaborative technical validation. | Reserve interface | Review draft ecological corridors and buffers | Reserve comments | 20 | Environment Lead | Ecological corridor notes
M06 | Royal Reserve Authority | Validate reserve interface, ecological corridors and watershed implications. | The previous meeting highlighted ecological continuity, watershed implications and the need for collaborative technical validation. | Watershed and hydrology | Discuss watershed impacts and potential downstream/reserve implications | Hydrology considerations | 20 | Hydrology Lead | Hydrology interface actions
M06 | Royal Reserve Authority | Validate reserve interface, ecological corridors and watershed implications. | The previous meeting highlighted ecological continuity, watershed implications and the need for collaborative technical validation. | Development scenarios | Review whether structure plan options create reserve-interface risks | Feedback on preferred direction | 20 | Urban Planning Lead | Scenario comments
M06 | Royal Reserve Authority | Validate reserve interface, ecological corridors and watershed implications. | The previous meeting highlighted ecological continuity, watershed implications and the need for collaborative technical validation. | Next steps | Agree technical validation process | Follow-up actions | 10 | Stakeholder Lead | MoM
M07 | MOMAH | Align Stage 4 structure plan with planning/housing policy and approved plans. | The previous MOMAH meeting raised land ownership, building status, compensation, approved plan integration and Plot No.2. | Stage 4 land-use direction | Present draft structure plan assumptions | Planning policy feedback | 15 | Urban Planning Lead | Land-use comments
M07 | MOMAH | Align Stage 4 structure plan with planning/housing policy and approved plans. | The previous MOMAH meeting raised land ownership, building status, compensation, approved plan integration and Plot No.2. | Housing and Plot No.2 | Confirm any housing-sector plans or ownership implications | Confirmation / information required | 15 | Urban Planning Lead | Housing note
M07 | MOMAH | Align Stage 4 structure plan with planning/housing policy and approved plans. | The previous MOMAH meeting raised land ownership, building status, compensation, approved plan integration and Plot No.2. | Approved plans integration | Discuss how approved plans are considered and where exceptions apply | Integration principles | 20 | Urban Planning Lead | Approved plan treatment note
M07 | MOMAH | Align Stage 4 structure plan with planning/housing policy and approved plans. | The previous MOMAH meeting raised land ownership, building status, compensation, approved plan integration and Plot No.2. | Compensation and building status | Clarify ministry expectations on affected plots and licensing issues | Input on compensation approach | 20 | Land / Legal Lead | Compensation comments
M07 | MOMAH | Align Stage 4 structure plan with planning/housing policy and approved plans. | The previous MOMAH meeting raised land ownership, building status, compensation, approved plan integration and Plot No.2. | Next steps | Agree materials for internal ministry review | Action closure dates | 10 | Stakeholder Lead | MoM
M08 | RIPC | Align infrastructure phasing, service provider coordination and funding model inputs. | The previous RIPC meeting highlighted service-provider coordination, KMZ verification, 5-year vision and funding model support. | Stage 4 infrastructure assumptions | Present utility and road infrastructure strategy | Scope of RIPC review | 15 | Infrastructure Lead | Review scope
M08 | RIPC | Align infrastructure phasing, service provider coordination and funding model inputs. | The previous RIPC meeting highlighted service-provider coordination, KMZ verification, 5-year vision and funding model support. | Service provider coverage | Confirm KMZ verification and target zones | Coverage feedback | 15 | GIS / Infrastructure Lead | Coverage note
M08 | RIPC | Align infrastructure phasing, service provider coordination and funding model inputs. | The previous RIPC meeting highlighted service-provider coordination, KMZ verification, 5-year vision and funding model support. | Phasing and delivery | Discuss 5-year plan alignment and pilot implementation lessons | Phasing recommendations | 20 | Infrastructure Lead | Phasing input
M08 | RIPC | Align infrastructure phasing, service provider coordination and funding model inputs. | The previous RIPC meeting highlighted service-provider coordination, KMZ verification, 5-year vision and funding model support. | Funding model | Understand applicable infrastructure financing mechanisms | Funding inputs / limitations | 20 | Cost Lead | Funding mechanism note
M08 | RIPC | Align infrastructure phasing, service provider coordination and funding model inputs. | The previous RIPC meeting highlighted service-provider coordination, KMZ verification, 5-year vision and funding model support. | Next steps | Agree whether additional provider meetings are needed | Stakeholder coordination route | 10 | Stakeholder Lead | MoM
M09 | Ministry of Industry and Mineral Resources | Clarify mineral/industrial constraints impacting Stage 4 developable land. | The project materials identify a silica/sand reserve near the project and previous coordination flagged Ministry of Industry as a key stakeholder. | Project context and Stage 4 purpose | Present draft constraints map and project boundary | Confirmation of review scope | 10 | Urban Planning Lead | Scope agreed
M09 | Ministry of Industry and Mineral Resources | Clarify mineral/industrial constraints impacting Stage 4 developable land. | The project materials identify a silica/sand reserve near the project and previous coordination flagged Ministry of Industry as a key stakeholder. | Mineral reserve boundaries | Confirm location, status and protection requirements for mineral/silica/sand reserves | Validated GIS layer or formal note | 25 | Environment / GIS Lead | Constraints map update
M09 | Ministry of Industry and Mineral Resources | Clarify mineral/industrial constraints impacting Stage 4 developable land. | The project materials identify a silica/sand reserve near the project and previous coordination flagged Ministry of Industry as a key stakeholder. | Industrial / resource plans | Clarify any future plans that may affect the site | Planning input or information required | 15 | Urban Planning Lead | Future plan note
M09 | Ministry of Industry and Mineral Resources | Clarify mineral/industrial constraints impacting Stage 4 developable land. | The project materials identify a silica/sand reserve near the project and previous coordination flagged Ministry of Industry as a key stakeholder. | Land-use implications | Discuss acceptable buffers, restrictions and incompatible land uses | Land-use constraints | 20 | Urban Planning Lead | Stage 4 constraint log
M09 | Ministry of Industry and Mineral Resources | Clarify mineral/industrial constraints impacting Stage 4 developable land. | The project materials identify a silica/sand reserve near the project and previous coordination flagged Ministry of Industry as a key stakeholder. | Next steps | Agree data sharing and follow-up timing | RFI and MoM | 10 | Stakeholder Lead | Action tracker
M10 | MOTLS / RGA / TGA / SAR | Validate Stage 4 movement network and regional transport interfaces. | Stage 4 must translate Riyadh Plan transport logic and baseline transport findings into a structure plan network. | Network overview | Present proposed road hierarchy and regional connections | Review scope confirmed | 15 | Transport Lead | Review scope
M10 | MOTLS / RGA / TGA / SAR | Validate Stage 4 movement network and regional transport interfaces. | Stage 4 must translate Riyadh Plan transport logic and baseline transport findings into a structure plan network. | ROW and planned corridors | Confirm planned alignments, ROW extents and any protected corridors | Transport GIS inputs | 20 | Transport Lead | Corridor action list
M10 | MOTLS / RGA / TGA / SAR | Validate Stage 4 movement network and regional transport interfaces. | Stage 4 must translate Riyadh Plan transport logic and baseline transport findings into a structure plan network. | Logistics and rail interfaces | Discuss Dammam Road, SAR, freight/logistics needs and future capacity | Transport constraints and opportunities | 20 | Transport Lead | Network comments
M10 | MOTLS / RGA / TGA / SAR | Validate Stage 4 movement network and regional transport interfaces. | Stage 4 must translate Riyadh Plan transport logic and baseline transport findings into a structure plan network. | Integration with land use | Confirm access strategy and mobility hierarchy for centers and development areas | Land-use/network feedback | 20 | Urban Planning + Transport | Integrated comments
M10 | MOTLS / RGA / TGA / SAR | Validate Stage 4 movement network and regional transport interfaces. | Stage 4 must translate Riyadh Plan transport logic and baseline transport findings into a structure plan network. | Next steps | Agree data and review timeline | Action closure dates | 10 | Stakeholder Lead | MoM
M11 | SPGA + MOJ | Close land ownership and title-deed gaps for Stage 4 parcel decisions. | Stage 2-3 identified dataset inconsistencies and the need for legal/title deed validation before parcel reassignment and land treatment. | Parcel data gaps | Present known title deed and parcel dataset inconsistencies | Validation scope agreed | 15 | Land Lead | Data gap register
M11 | SPGA + MOJ | Close land ownership and title-deed gaps for Stage 4 parcel decisions. | Stage 2-3 identified dataset inconsistencies and the need for legal/title deed validation before parcel reassignment and land treatment. | Ownership confirmation | Confirm state-owned lands and private/title deed status | Updated ownership data | 25 | Land / Legal Lead | Ownership action list
M11 | SPGA + MOJ | Close land ownership and title-deed gaps for Stage 4 parcel decisions. | Stage 2-3 identified dataset inconsistencies and the need for legal/title deed validation before parcel reassignment and land treatment. | Affected parcels | Discuss parcels impacted by wadis, pipelines and no-go zones | Legal treatment requirements | 20 | Land / Legal Lead | Affected parcel log
M11 | SPGA + MOJ | Close land ownership and title-deed gaps for Stage 4 parcel decisions. | Stage 2-3 identified dataset inconsistencies and the need for legal/title deed validation before parcel reassignment and land treatment. | Methodology alignment | Confirm methodology for land reassignment and legal constraints | Methodology comments | 15 | Legal Lead | Methodology decision note
M11 | SPGA + MOJ | Close land ownership and title-deed gaps for Stage 4 parcel decisions. | Stage 2-3 identified dataset inconsistencies and the need for legal/title deed validation before parcel reassignment and land treatment. | Next steps | Agree data handover and closure dates | Formal RFI and MoM | 10 | Stakeholder Lead | Action tracker
M12 | Utilities Cluster | Validate Stage 4 wet, dry and digital utility assumptions. | Baseline identified major infrastructure gaps; Stage 4 requires demand, network and cost assumptions for the structure plan and feasibility interface. | Utility demand assumptions | Review preliminary demand rates and phasing | Agreement or correction | 20 | Utilities Leads | Demand assumptions log
M12 | Utilities Cluster | Validate Stage 4 wet, dry and digital utility assumptions. | Baseline identified major infrastructure gaps; Stage 4 requires demand, network and cost assumptions for the structure plan and feasibility interface. | Network capacity and standards | Confirm standards and capacity limitations | Standards and capacity register | 20 | Utilities Leads | Input register
M12 | Utilities Cluster | Validate Stage 4 wet, dry and digital utility assumptions. | Baseline identified major infrastructure gaps; Stage 4 requires demand, network and cost assumptions for the structure plan and feasibility interface. | Corridor integration | Review utility corridors, ROW and conflicts with wadis/pipelines | Conflict log | 15 | GIS / Utilities Lead | Constraint updates
M12 | Utilities Cluster | Validate Stage 4 wet, dry and digital utility assumptions. | Baseline identified major infrastructure gaps; Stage 4 requires demand, network and cost assumptions for the structure plan and feasibility interface. | Cost assumptions | Review unit rates and cost estimate basis | Cost review comments | 20 | Cost / Utilities Lead | Cost inputs
M12 | Utilities Cluster | Validate Stage 4 wet, dry and digital utility assumptions. | Baseline identified major infrastructure gaps; Stage 4 requires demand, network and cost assumptions for the structure plan and feasibility interface. | Next steps | Agree data and review cycle | Action tracker | 10 | Stakeholder Lead | MoM

## 03_Scheduling priority
PEG Stage 3 - 4Stakeholder Coordination plan
Note: preparing ppt for each stakeholder take 2 working days and then send it to the client before the meeting to reivew , 1 working day for client review, then finalize and hold the meeting.( total 4 days)
Total meetings in tracker |  |  |  |  | Primary Stage 3-4 meetings | [7 empty] | Meetings completed In the past stages
8 |  |  |  |  | 4 | [7 empty] | 14
Seq | Priority | Track | Stakeholder | Contact person | Responsibility Snapshot | Meeting Objective | Key Output | Proposed Week | Meeting Date | Draft to Client | Final Deck | MOM Due | Lubna/Hind Request | Status | Owner | Notes / Dependencies
4 | High | Supporting Coordination | Ministry of Energy | Faisal Alsununi Ministry representative faisal.alsununi@moenrgy.gov.sa Mohmeed Alshaikh Ministry representative Mohmeed.Alshaikh@moenergy.gov.sa | Provide A feedback | Confirm strategic assumptions relevant to Project East Grant utilities planning and costing, and maintain periodic coordination meetings as agreed during the latest meeting. | Energy policy assumptions log | Week 2 | 2026-09-27 | 2026-07-16 | 2026-09-25 | 2026-09-28 | Not sent | Not started | Molham (WSP)
5 | High | Supporting Coordination | Saudi Energy (SE) | Faisal Alsununi Ministry representative faisal.alsununi@moenrgy.gov.sa Mohmeed Alshaikh Ministry representative Mohmeed.Alshaikh@moenergy.gov.sa | Provide A feedback | Confirm latest electricity standards, available data and cost assumptions | Validated SEC assumptions and inputs | Week 2 | 2026-09-27 | 2026-07-16 | 2026-09-25 | 2026-09-28 | Not sent | Not started | Molham (WSP)
6 | High | Supporting Coordination | Saudi Aramco | Faisal Alsununi Ministry representative faisal.alsununi@moenrgy.gov.sa Mohmeed Alshaikh Ministry representative Mohmeed.Alshaikh@moenergy.gov.sa | Pipelines, corridors, and technical approvals | Review pipeline constraints and protection requirements strategic assumptions relevant to Project Eat Grant utilities planning and costing | Pipeline constraints and approval requirements | Week 2 | 2026-09-27 | 2026-07-16 | 2026-09-25 | 2026-09-28 | Not sent | Not started | Molham (WSP)
7 | High | Supporting Coordination | Saudi Electricity Regulatory Authority (SERA) | Faisal Alsununi Ministry representative faisal.alsununi@moenrgy.gov.sa Mohmeed Alshaikh Ministry representative Mohmeed.Alshaikh@moenergy.gov.sa | Electricity regulations and service standards | Align on regulatory requirements and service standards | Regulatory guidance and compliance requirements | Week 2 | 2026-09-27 | 2026-07-16 | 2026-09-25 | 2026-09-28 | Not sent | Not started | Molham (WSP)
8 | High | Supporting Coordination | MEWA | Mohammed bin Saleh Al-Duhaim Executive Director of Geospatial Data maldohim@swa.gov.sa Abdulrahman bin Mohammed Al-Shehri Director General of Project Services amshehri@nwc.com.sa Naif bin Mutlaq Al-Dulaie Deputy Director of the Office of the Undersecretary for Lands and Geospatial Information naimalotaibi@mewa.gov.sa | National counterpart for water, environment and agriculture matters affecting hydrology, irrigation and environmental baselines | National counterpart for water, environment, and agriculture matters, ensuring alignment with the National Water Strategy and relevant sector priorities, coordinating on hydrology, irrigation, and environmental baselines, and reviewing available project data with the entity to identify and reconcile any discrepancies. | Validated MEWA assumptions and data needs | Week 2 | 2026-09-30 | 2026-07-19 | 2026-09-29 | 2026-10-01 | Not sent | Not started | Molham (WSP)
9 | High | Supporting Coordination | National Water Company (NWC) | Mohammed bin Saleh Al-Duhaim Executive Director of Geospatial Data maldohim@swa.gov.sa Abdulrahman bin Mohammed Al-Shehri Director General of Project Services amshehri@nwc.com.sa Naif bin Mutlaq Al-Dulaie Deputy Director of the Office of the Undersecretary for Lands and Geospatial Information naimalotaibi@mewa.gov.sa | Operating counterpart for water supply, wastewater and service delivery assumptions | National counterpart for water, environment, and agriculture matters, ensuring alignment with the National Water Strategy and relevant sector priorities, coordinating on hydrology, irrigation, and environmental baselines, and reviewing available project data with the entity to identify and reconcile any discrepancies. | Validated NWC assumptions and inputs | Week 2 | 2026-09-30 | 2026-07-19 | 2026-09-29 | 2026-10-01 | Not sent | Not started | Molham (WSP)
10 | high | Supporting Coordination | Saudi Water Authority (SWA) | Mohammed bin Saleh Al-Duhaim Executive Director of Geospatial Data maldohim@swa.gov.sa Abdulrahman bin Mohammed Al-Shehri Director General of Project Services amshehri@nwc.com.sa Naif bin Mutlaq Al-Dulaie Deputy Director of the Office of the Undersecretary for Lands and Geospatial Information naimalotaibi@mewa.gov.sa | Water policies, resources, and infrastructure planning | National counterpart for water, environment, and agriculture matters, ensuring alignment with the National Water Strategy and relevant sector priorities, coordinating on hydrology, irrigation, and environmental baselines, and reviewing available project data with the entity to identify and reconcile any discrepancies. | Water policy and infrastructure guidance | Week 2 | 2026-09-30 | 2026-07-19 | 2026-09-29 | 2026-10-01 | Not sent | Not started | Molham (WSP) | Useful before Stage 4 utilities consolidation
11 | high | Supporting Coordination | Saudi Irrigation Organization (SIO) | Mohammed bin Saleh Al-Duhaim Executive Director of Geospatial Data maldohim@swa.gov.sa Abdulrahman bin Mohammed Al-Shehri Director General of Project Services amshehri@nwc.com.sa Naif bin Mutlaq Al-Dulaie Deputy Director of the Office of the Undersecretary for Lands and Geospatial Information naimalotaibi@mewa.gov.sa | Irrigation systems and water efficiency | Review irriNational counterpart for water, environment, and agriculture matters, ensuring alignment with the National Water Strategy and relevant sector priorities, coordinating on hydrology, irrigation, and environmental baselines, and reviewing available project data with the entity to identify and reconcile any discrepancies.gation opportunities and water reuse potential | Irrigation and water reuse recommendations | Week 2 | 2026-09-30 | 2026-07-19 | 2026-09-29 | 2026-10-01 | Not sent | Not started | Molham (WSP) | Review irrigation and water reuse opportunities.
Formulas:
Final Deck = IF(ISBLANK([Meeting Date]),"",WORKDAY([Meeting Date],-1))
MOM Due = IF(ISBLANK([Meeting Date]),"",WORKDAY([Meeting Date],1))
Note on A4: Total meetings in tracker
Note on F4: Primary Stage 3 meetings
Note on N4: Meetings completed
Note on J7: User input: enter the confirmed meeting date. All working dates on the right update automatically.
Note on N7: Track whether Lubna has formally requested / confirmed the meeting.
Note on O7: Use the dropdown to track the live status of each meeting.

## 04_Previous Tracker
Previous Meetings and Follow-up Tracker
Only information available from the provided MoMs is recorded. Blank owners/dates are marked as Information Required or Open - verify status.
S.No | Stakeholder Type | Description | Stakeholder | Date of Engagement | Key Point Discussed | Action Items | Minutes of meeting | Minutes of meeting2 | Minutes of meeting3 | Minutes of meeting4 | Minutes of meeting5 | Minutes of meeting6 | Minutes of meeting7 | Minutes of meeting8 | follow-up | their response note | Our Actions
1 | External | Coordination and alignment meeting – East Riyadh Grant Project – AMANAH | Riyadh Municipality (Amanah) | 2026-02-16 | - Discussed Project East Grant overview and stakeholder coordination between RCRC and Amanah. | - Amanah to share complete parcel dataset (51k+ records) for baseline validation. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/03.%20AMANAH/260216-55007720-PR-%20Amanah%20Stakeholder%20Engagement%20and%20Data%20Validation%20(EN).docx?d=w385edf31370d4d74907d3a2e798f4e34&csf=1&web=1&e=ec9Z19 | [7 empty] | Done | Reviewed and logged the received GIS land data for further assessment and integration into the project records. | A follow-up coordination meeting has been scheduled for next Monday to review the submitted data, discuss outstanding items, and follow up on any pending requirements.
[5 empty] | - Identified major data gaps, with ~6,000+ parcels missing grant status and need for full dataset (51k+). | - Arrange coordination meeting with Ministry of Justice for ownership verification.
[5 empty] | - Reviewed land ownership and land-use issues, including industrial zones and government-owned lands. | - Share and review Aramco pipeline buffer study for affected lands.
[5 empty] | - Highlighted need for ownership validation with Ministry of Justice. | - Continue technical coordination on hydrology, planning, and infrastructure inputs.
[5 empty] | - Noted project and permit suspensions due to Royal Decree and pipeline constraints. | - Provide additional details on industrial permits and land-use approvals.
[5 empty] | - Agreed on next steps: data submission, MoJ coordination, and further technical studies (hydrology, planning). | - Align stakeholders on next steps to address project and permit constraints.
2 | External | Coordination and alignment meeting – East Riyadh Grant Project – Ministry of Justice | Ministry of Justice | 2026-02-25 | - Meeting focused on coordination with the Ministry of Justice for Project East Grant and clarification of title deed issues. | - MoJ to review and verify title deed status for ~13,851 parcels. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/04.%20MOJ/260225-55007720-MB-MOJ%20Coordination%20Meeting%20(EN).docx?d=w5dcc8904ef8a4fa990e51a7c67142970&csf=1&web=1&e=jaPVgj | [7 empty] | Done | A coordination meeting was held with the Ministry of Justice regarding land title deeds. The Ministry provided details of the plots associated with existing title deeds. | No further meetings are required at this stage. Additional coordination sessions will be arranged with the Ministry of Justice if requested by the legal team or as needed to support the project's requirements.
[5 empty] | - Around 13,851 parcels are under review for title deed status, requiring classification verification | - RCRC/Amanah to submit detailed parcel dataset (Excel + maps) for verification.
[5 empty] | - Discussed constraints in title deed issuance, including Mayor approval and classification as public service land | - Both parties to align on parcel classification (public service, grant, etc.).
[5 empty] | - Highlighted data submission requirements, including detailed Excel dataset and supporting maps | - MoJ to investigate legal/judicial discrepancies impacting ownership records.
[5 empty] | - Noted potential legal/judicial discrepancies due to cases filed outside Riyadh | - Establish clear process for title deed issuance approvals (including Mayor approval where required).
[5 empty] | - Agreed on data sharing approach and timeline, with MoJ to provide data within 3–4 weeks | - MoJ to share verified data within agreed timeline (3–4 weeks).
3 | External | Coordination and alignment meeting – East Riyadh Grant Project – SPGA | State Properties General Authority | 2026-03-03 | - Meeting focused on coordination with the General Authority for State Properties (GASP) for Project East Grant master plan update. | - RCRC to share project data (Shape files, KMZ, and presentation) with SGPA for review. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/05.%20State%20Properties%20General%20Authority%20(SPGA)/260303-55007720-MB-SPGA%20Coordination%20Meeting%20(EN).docx?d=w954ab0d40eba4b239b390cacee6adc9a&csf=1&web=1&e=46vgUf | [7 empty] | Done | SPGA responded with: • ZIP file containing GIS shapefiles (Lands.shp) with government land parcels data • Includes: polygon boundaries, area calculations, and land classification | Share GIS data with WSP GIS team for integration into project basemap
[5 empty] | - Discussed legal and regulatory status of governmental lands, including classification and allocation types | - SGPA to review and confirm legal status and classification of government lands.
[5 empty] | - Raised queries on ownership transfer, title deeds, and land use across multiple plans (3141, 3210, 3143) | - Both parties to clarify ownership transfer and title deed requirements for key plans.
[5 empty] | - Covered issues related to government lands outside development boundary and potential land replacement | - Assess lands outside development boundary and identify possible replacements if required.
[5 empty] | - GASP requested project data files (Shape, KMZ, presentation) for review | - Align on land use and allocation status across affected parcels.
[5 empty] | - Agreed on timeline for data submission and response (within 1 week) to proceed with validation | -SGPA to provide feedback within the agreed timeline (about 1 week) to proceed further.
4 | External | Coordination and alignment meeting – East Riyadh Grant Project – Ministry of Industry and Mineral Resources. | Ministry of Industry and Mineral Resources | 2026-04-15 | - Meeting covered Project East Grant overview, including objectives, scope, and alignment with the Riyadh strategic plan. | - MIM to review project data and assess impact on silica zones and industrial activities. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/06.%20MIM/260225-55007720-MB-MIMCoordination%20Meeting.docx?d=w205fc03470964c928752fdda6cffe0fc&csf=1&web=1&e=VZLZzS | [7 empty] | RP | Ministry responded via email with 2 maps showing mining areas that overlap with the project. They request excluding these areas from the project. | Share with WSP team and coordinate with RCRC on boundary adjustments
[5 empty] | - Highlighted the large project area and need to assess both current overlaps and future development impacts. | - RCRC to share detailed project data and overlap analysis with MIM.
[5 empty] | - Confirmed overlap with the silica area, which includes key industrial activities like cement and ceramics. | - Both parties to evaluate constraints related to protected silica resources.
[5 empty] | - Noted that the silica zone is strategically important and protected, being the Kingdom’s primary raw material source | - Align on future land use, industrial planning, and development vision for the area.
[5 empty] | - Discussed future industrial activities, development vision, and workforce accommodation needs. | - Assess workforce accommodation and infrastructure requirements.
[5 empty] | - Agreed on data sharing and further review by the Ministry, followed by feedback and continued coordination. | - Continue coordination with MIM and provide feedback for further planning decisions.
5 | External | Coordination and alignment meeting – East Riyadh Grant Project – Imam Abdulaziz Bin Muhammad Royal Reserve | Imam Abdulaziz Bin Muhammad Royal Reserve | 2026-05-04 | - Meeting focused on alignment between Project East Grant and Imam Abdulaziz Royal Reserve, covering planning and environmental coordination. | - RCRC to share updated planning data and interface details with the Royal Reserve team. | https://wsponlineare.sharepoint.com/:b:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/07.%20Imam%20Abdulaziz%20Bin%20Muhammad%20Royal%20Reserve/260504-55007720-PR-Project%20East%20Grant%20Coordination%20,%20alignment%20with%20the%20Imam%20Abdulaziz%20bin%20Muhammad%20Royal%20Reserve%20%E2%80%93%20East%20Riyadh%20Grants%20Project.pdf?csf=1&web=1&e=H3TG02 | [7 empty] | Done | . The Ministry identified overlaps between the project boundary and mining reserve areas, particularly high-purity silica reserves, and recommended excluding these areas from the project. *Excel file: Detailed answers to 26 technical questions (buffer zones, wadis, ecology, etc.) • PDF file: Project implementation guidelines for Royal Reserve | Share IARDA responses with WSP technical team for review and integration into project design
[5 empty] | - Project spans ~550–584 sq. km, aiming to improve urban planning, infrastructure, and development strategy. | - Royal Reserve to review spatial overlaps and environmental constraints (biodiversity, corridors, buffers).
[5 empty] | - Emphasis on environmental sustainability, including hydrology, flood management, and biodiversity integration with the reserve. | - Both parties to align on hydrology and flood management requirements across the interface areas.
[5 empty] | - Highlighted key challenges: lack of infrastructure, outdated land plans, environmental constraints, and multi-agency coordination issues. | - Track and resolve open technical queries through a shared Excel log.
[5 empty] | - Discussed technical aspects such as ecological corridors, watershed impacts, and future growth scenarios (15–20 years). | - Coordinate on land use, development boundaries, and protected zones to avoid conflicts.
[5 empty] | - Agreed on next steps, including data sharing, query tracking via Excel, and continued stakeholder coordination for validation. | - Continue multi-stakeholder coordination and validation meetings for project alignment.
6 | External | Coordination and alignment meeting – East Riyadh Grant Project – MEWA | Ministry of Environment, Water and Agriculture | 2026-05-05 | - Meeting focused on strategic coordination with MEWA for the East Riyadh Grants Project, including alignment on environmental and water-sector requirements. | - MEWA to share standard templates and environmental assessment frameworks with RCRC/WSP. | https://wsponlineare.sharepoint.com/:b:/r/sites/SA-Project-Grant-RCR/Shared%20Documents/02-PM%20Docs/02-%20MoM/02-Outgoing/00.%20Client%20Meetings/08.%20MEWA/260505-55007720-MB-MEWA-MoM-.pdf?csf=1&web=1&e=HAUrkG | [7 empty] | DMO | رCoordination with DMO is required to address the relevant matters and obtain the necessary information | رCoordination with DMO is required to address the relevant matters and obtain the necessary information
[5 empty] | - MEWA emphasized the need for strategic-level coordination aligned with ministry frameworks and confirmed availability of standard templates. | - RCRC/WSP to review and align submissions with MEWA’s requirements and guidelines.
[5 empty] | - Discussed environmental assessment requirements, with MEWA providing models expected to address key project queries | - Both parties to coordinate on environmental studies and impact assessments for the project.
[5 empty] | - Project team presented key technical topics requiring MEWA input, including environmental and planning aspects. | - Align on water-sector planning, infrastructure integration, and future demand requirements.
[5 empty] | - Highlighted importance of future coordination on water-sector planning and integration. | - Project team to address key technical queries raised by MEWA.
[5 empty] | - Agreed on next steps, including template sharing, review by RCRC/WSP, and continued coordination meetings. | - Continue regular coordination meetings to ensure alignment and timely feedback.
7 | External | Coordination and alignment meeting – East Riyadh Grant Project – Ministry of Energy | Ministry of Energy | 2026-05-11 | - Project East Grant is a large-scale master planning initiative in eastern Riyadh (~584 km²), currently in Stage 03, focused on developing a sustainable, infrastructure-integrated urban framework. | - WSP to prepare and share presentation along with consolidated questions in Excel format for MoE review. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7B3F7293F7-F397-41A5-B207-4D0D4CF09274%7D&file=260511-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20%25u2013%20East%20Riyadh%20Grant%20Project%20%25u2013%20Ministry%20of%20Energy.docx&action=default&mobileredirect=true | [7 empty] | Done | A follow-up coordination meeting has been agreed upon to discuss outstanding matters and next steps. | Conducted a second coordination meeting to follow up on outstanding matters and discuss the latest updates.
[5 empty] | - Ministry of Energy confirmed that all upcoming meetings shall be conducted in Arabic; queries to be submitted via presentation + Excel document for structured response. | - WSP to arrange future meetings ensuring Arabic language requirement is addressed.
[5 empty] | - Alignment on strategic energy infrastructure and corridor protection requirements; understand impact on land use, phasing, and development feasibility. | - MoE to provide clarification on pipeline alignment, protection zones, and land use restrictions.
[5 empty] | - Saudi Aramco pipeline identified as key strategic corridor requiring protection; critical confirmations needed on alignment, protection zones, setbacks, and permitted land uses. | - MoE to assess feasibility of undergrounding or rerouting high-voltage transmission lines.
[5 empty] | - Power infrastructure (transmission lines and substations) may impact land suitability; query raised on feasibility of undergrounding or rerouting high-voltage overhead lines. | - MoE to share detailed electricity demand forecasts, load requirements, and grid reinforcement plans.
[5 empty] | - Further alignment required with Ministry of Energy, Saudi Aramco, Saudi Electricity Company (SEC), and National Grid for electricity demand and network planning. | - All parties to continue coordination and participate in workshop on 21 May; align development plans with energy infrastructure constraints.
8 | External | Technical Meeting – East Riyadh Grant Project – Riyadh Municipality (General Directorate of Stormwater Networks) | Riyadh Municipality (Amanah) | 2026-06-18 | - Technical meeting with Riyadh Municipality's Flood Management Department to review available Amanah hydrological study, understand methodology, identify data gaps, and request updated information. | - Riyadh Municipality to share available HEC-HMS and HEC-RAS model files related to previous Amanah study. | 260618-55007720-PR-Project East Grant -Technical Meeting – East Riyadh Grant Project – Riyadh Municipality (General Directorate of Stormwater Networks_v2 1.docx | [7 empty] | Done | The data has been reviewed and documented. No further meetings are required at this stage, as all available data has already been received. | The WSP Hydrology team will utilize the received data as part of their assessment. Further coordination with the Flood Management Department will be initiated if additional discussions or clarifications are required.
[5 empty] | - Municipality clarified that previous Amanah study is over 12 years old, covered only limited portion of project area, and should not be relied on for current decision-making. | - Riyadh Municipality to share reports, drawings, and data related to important wadis in the project area.
[5 empty] | - WSP requested updated survey data, hydrological data, HEC-HMS/HEC-RAS files, and GIS layers; Municipality confirmed they will share available data but noted it may be old and based on Ain Al-Abd coordinate system. | - Riyadh Municipality to share information on existing culverts, stormwater infrastructure, and spot levels.
[5 empty] | - Strategic hydrology studies exist but are not yet approved and may not be shareable; previous studies recommended conducting a dedicated hydrological study for the area. | - WSP to review received data and confirm accuracy, coordinate system, and relevance to Project East Grant.
[5 empty] | - WSP presented baseline hydrology assessment using available topographic data (DEM 10m) and Google Earth imagery; key challenge is lack of complete spatial data for wadi protection and flood behavior. | - WSP to use Amanah's previous study only as methodology reference, not as final technical basis.
[5 empty] | - Municipality will share available hydrology-related information including culvert locations, stormwater infrastructure, and wadi studies within approximately one month. | - Continue coordination with Riyadh Municipality on hydrology, wadi buffers, flood management, and data requirements.
9 | External | Coordination and alignment meeting – East Riyadh Grant Project –Ministry of Transport & Logistics | Ministry of Transport and Logistics Services | 2026-05-13 | - Meeting focused on strategic coordination with Ministry of Transport & Logistics Services for the East Riyadh Grant Project, covering transport network planning and future road infrastructure. | - MOTLS to share detailed transport network plans and road hierarchy data with RCRC/WSP. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7BC679ADB2-2B7E-46CB-96B2-68AC75FD8BC9%7D&file=260513-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20%25u2013%20East%20Riyadh%20Grant%20Project%20%25u2013%20Ministry%20of%20Transport%20and%20Logistics%20Services.docx&action=default&mobileredirect=true | [7 empty] | Done | The entity expressed its willingness to provide any required support or assistance throughout the project. | No further meetings are required at this stage. A follow-up meeting may be required upon completion of Stage 3 (Options Assessment) to review the outcomes and discuss any further requirements.
[5 empty] | - Discussed regional and local road network hierarchy, including planned expressways, arterial roads, and connections to neighboring developments. | - RCRC/WSP to review transport data and integrate into master plan development.
[5 empty] | - Highlighted existing and planned road corridors affecting the project area, including Ring Road extensions and major interchanges. | - Both parties to align on public transport corridors and mobility hub locations.
[5 empty] | - Reviewed public transport integration requirements, including metro extensions, bus rapid transit (BRT) corridors, and mobility hubs. | - MOTLS to provide freight corridor requirements and logistics zone constraints.
[5 empty] | - Discussed freight and logistics considerations, including truck routes, logistics zones, and buffer requirements for residential areas. | - Coordinate on road infrastructure phasing and implementation timeline.
[5 empty] | - Agreed on data sharing approach and timeline, with MOTLS to provide transport network data and future planning inputs for integration. | - Continue regular coordination meetings to ensure alignment with transport planning requirements.
10 | External | Coordination and alignment meeting – East Riyadh Grant Project –Ministry of Municipalities and Housing | Ministry of Municipalities and Housing | 2026-05-14 | - Meeting focused on coordination with Ministry of Municipalities and Housing for Project East Grant, covering project scope, objectives, and development challenges. | - RCRC to share KMZ file and presentation slides with Ministry for internal review. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7B2A2A3704-6610-40DD-8A99-26379BECA73E%7D&file=260514-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20-%20Ministry%20of%20Municipalities%20and%20Housing.docx&action=default&mobileredirect=true | [7 empty] | Done | The entity welcomed continued collaboration and expressed its readiness to provide any required support or assistance throughout the project | A follow-up coordination meeting is scheduled for Monday, 26 July, to discuss progress, review outstanding items, and align on the next steps.
[5 empty] | - WSP presented technical overview including existing site conditions, available datasets, and proposed future vision and development direction. | - Provide clarifications on land ownership status and Plot No. 2 (housing sector confirmation).
[5 empty] | - Ministry raised key queries on land ownership (MoJ involvement), building licensing status (licensed vs unlicensed), and construction activities post Royal Decree. | - Address Ministry queries on building licensing status (licensed vs unlicensed).
[5 empty] | - RCRC clarified data sources include State Properties General Authority, Ministry of Justice, and Riyadh Municipality; confirmed majority of buildings are unlicensed with some valid permits. | - Clarify development status and construction activities post Royal Decree.
[5 empty] | - Discussed compensation mechanism and integration of existing approved plans, with exceptions for wadi systems, environmental conditions, and infrastructure constraints (e.g., Aramco pipelines). | - Define and communicate compensation approach, including alternative land provision where feasible.
[5 empty] | - Ministry confirmed willingness to support the project and requested sharing of presentation materials (KMZ, slides) for internal review. | - Ministry to review shared materials and align on future land use plans within project area.
11 | External | Coordination and Alignment Meeting for the East Riyadh Land Grants Project – Wadi Al-Sulai | Wadi Al-Sulai | 2026-05-18 | - Meeting focused on coordination between East Riyadh Grants Project and Wadi Al-Sulai, covering wadi protection, affected plots, development controls, and compensation mechanisms. | - WSP/RCRC to update hydrological study for Project East Grant to support planning and design decisions. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7B26526378-0E57-44DF-861B-C3631B2097A9%7D&file=260518-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20%25u2013%20East%20Riyadh%20Grants%20Project%20%25u2013%20Wadi%20Al-Sulai.docx&action=default&mobileredirect=true | [7 empty] | Done | A technical meeting was held with the Hydrology team, and the requested data was provided. | The WSP Hydrology team will continue direct coordination as required. Additional information will be requested in the future if needed to support the ongoing assessment and project
[5 empty] | - WSP presented baseline findings; wadis intersect existing developments and planned land uses, with general hydrological direction identified and need for updated technical studies. | - Coordinate with Riyadh Municipality land and property departments regarding affected lands and compensation mechanisms.
[5 empty] | - Wadi buffers must be defined case-by-case based on hydrology, depth, landscape, environmental conditions, and urban design; not fixed distances. | - Request available environmental and vegetation studies from Wadi Al Sulai Project team; clarify land ownership for Plot No. 2.
[5 empty] | - Wadi diversion possible only in limited cases with strong justification; natural alignment should be preserved and protection takes priority over development. | - WSP to review Wadi Al Sulai buffer approach and assess its relevance to Project East Grant.
[5 empty] | - Environmental studies include vegetation, wildlife, and ecological habitats; wadi classifications cover environmental wadi areas, urban wadi areas, and protection zones. | - Continue technical coordination with Wadi Al Sulai team in future meetings.
[5 empty] | - Land treatment depends on ownership status: approved subdivisions eligible for compensation/planning adjustments; unapproved subdivisions subject to removal; complex cases escalated to Riyadh Principality. | - Establish governance framework for wadi protection including monitoring, enforcement, and coordination with government entities.
12 | External | Coordination and Alignment Meeting – East Riyadh Land Grants Project – Riyadh Region Municipality – General Department | Riyadh Region Municipality | 2026-06-18 | - Technical meeting with Riyadh Municipality's Flood Management Department to review available Amanah hydrological study, understand methodology, identify data gaps, and request updated information. | - Riyadh Municipality to share available HEC-HMS and HEC-RAS model files related to previous Amanah study. | https://wsponlineare.sharepoint.com/sites/SA-Project-Grant-RCR/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSA%2DProject%2DGrant%2DRCR%2FShared%20Documents%2F02%2DPM%20Docs%2F02%2D%20MoM%2F02%2DOutgoing%2F00%2E%20Client%20Meetings%2F03%2E%20AMANAH%2F260618%2D55007720%2DPR%2DProject%20East%20Grant%20%2DTechnical%20Meeting%20%E2%80%93%20East%20Riyadh%20Grant%20Project%20%E2%80%93%20Riyadh%20Municipality%20%28General%20Directorate%20of%20Stormwater%20Networks%5Fv2%201%2Epdf&parent=%2Fsites%2FSA%2DProject%2DGrant%2DRCR%2FShared%20Documents%2F02%2DPM%20Docs%2F02%2D%20MoM%2F02%2DOutgoing%2F00%2E%20Client%20Meetings%2F03%2E%20AMANAH | [7 empty] | Done | A technical meeting was held with the Hydrology team, and the requested data was provided. | The WSP Hydrology team will continue direct coordination as required. Additional information will be requested in the future if needed to support the ongoing assessment and project
[5 empty] | - Municipality clarified that previous Amanah study is over 12 years old, covered only limited portion of project area, and should not be relied on for current decision-making. | - Riyadh Municipality to share reports, drawings, and data related to important wadis in the project area.
[5 empty] | - WSP requested updated survey data, hydrological data, HEC-HMS/HEC-RAS files, and GIS layers; Municipality confirmed they will share available data but noted it may be old and based on Ain Al-Abd coordinate system. | - Riyadh Municipality to share information on existing culverts, stormwater infrastructure, and spot levels.
[5 empty] | - Strategic hydrology studies exist but are not yet approved and may not be shareable; previous studies recommended conducting a dedicated hydrological study for the area. | - WSP to review received data and confirm accuracy, coordinate system, and relevance to Project East Grant.
[5 empty] | - WSP presented baseline hydrology assessment using available topographic data (DEM 10m) and Google Earth imagery; key challenge is lack of complete spatial data for wadi protection and flood behavior. | - WSP to use Amanah's previous study only as methodology reference, not as final technical basis.
[5 empty] | - Municipality will share available hydrology-related information including culvert locations, stormwater infrastructure, and wadi studies within approximately one month. | - Continue coordination with Riyadh Municipality on hydrology, wadi buffers, flood management, and data requirements.
13 | External | Coordination and Alignment Meeting – East Riyadh Grant Project – Riyadh Infrastructure Projects Centre | Riyadh Infrastructure Projects Centre (RIPC) | 2026-05-12 | - Project is a large-scale development initiative in East Riyadh requiring integrated infrastructure and master planning; RIPC highlighted similar project in Al Khair District (North Riyadh). | - Share project presentation, detailed information, and queries in Excel format with RIPC. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7BF59CD891-8130-4BF7-B8E8-C6816561469A%7D&file=260512-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20%20East%20Riyadh%20Grant%20Project%20%20Riyadh%20Infrastructure%20Projects%20Centre%20(002).docx&fromShare=true&action=default&mobileredirect=true | [7 empty] | DMO | Further coordination with DMO is required to obtain additional information and address outstanding matters. | Engagement with DMO will be required to follow up on outstanding matters and obtain any additional information needed to support the next phase of the assessment.
[5 empty] | - RIPC advised early coordination with Municipality to obtain approvals before proceeding; mentioned strong funding mechanism model that can be shared post-approval. | RCRC TO share kmz file of pg bundary
[5 empty] | - Key site constraints identified: Saudi Aramco pipeline (with protection buffers), multiple high-voltage transmission lines (380kV & 132kV), and strategic Dammam Road capacity risks. | - RIPC to share masterplan strategy and 5-year regional planning vision.
[5 empty] | - Other constraints include water transmission infrastructure from Eastern Province, silica reserves (Ministry of Industry), military zone in north-east, and proposed waste management zones. | - Coordinate with Municipality for approvals and participation in the project.
[5 empty] | - Limited enabling infrastructure observed: poor road network coverage, limited utilities (telecom, MV/LV power), minimal street lighting/CCTV, and residents rely on water tank supply instead of network. | - RIPC to provide details of funding mechanism and applicability to project; explore infrastructure financing models.
[5 empty] | - Riyadh has a 5-year comprehensive development plan aligned with service provider strategies; KMZ submission required to assess service coverage and infrastructure planning. | - Arrange follow-up meetings with Municipality and key stakeholders; validate infrastructure coverage based on service provider strategies.
14 | External | Coordination and Alignment Meeting – East Riyadh Land Grants Project – Ministry of Energy | Ministry of Energy | 2026-05-11 | - Project East Grant is a large-scale master planning initiative in eastern Riyadh (~584 km²), currently in Stage 03, focused on developing a sustainable, infrastructure-integrated urban framework. | - WSP to prepare and share presentation along with consolidated questions in Excel format for MoE review. | https://wsponlineare.sharepoint.com/:w:/r/sites/SA-Project-Grant-RCR/_layouts/15/Doc.aspx?sourcedoc=%7B3F7293F7-F397-41A5-B207-4D0D4CF09274%7D&file=260511-55007720-PR-Project%20East%20Grant%20Coordination%20and%20Alignment%20Meeting%20%25u2013%20East%20Riyadh%20Grant%20Project%20%25u2013%20Ministry%20of%20Energy.docx&action=default&mobileredirect=true | [7 empty] | Done | A second coordination meeting was held, and the relevant project information and supporting files were shared. Further coordination will take place upon completion of the current project stage | Agreed to establish regular coordination meetings to ensure continuous alignment, monitor progress, and address any emerging matters.
[5 empty] | - Ministry of Energy confirmed that all upcoming meetings shall be conducted in Arabic; queries to be submitted via presentation + Excel document for structured response. | RCRC TO share kmz file of pg bundary
[5 empty] | - Alignment on strategic energy infrastructure and corridor protection requirements; understand impact on land use, phasing, and development feasibility. | - MoE to provide clarification on pipeline alignment, protection zones, and land use restrictions.
[5 empty] | - Saudi Aramco pipeline identified as key strategic corridor requiring protection; critical confirmations needed on alignment, protection zones, setbacks, and permitted land uses. | - MoE to assess feasibility of undergrounding or rerouting high-voltage transmission lines.
[5 empty] | - Power infrastructure (transmission lines and substations) may impact land suitability; query raised on feasibility of undergrounding or rerouting high-voltage overhead lines. | - MoE to share detailed electricity demand forecasts, load requirements, and grid reinforcement plans.
[5 empty] | - Further alignment required with Ministry of Energy, Saudi Aramco, Saudi Electricity Company (SEC), and National Grid for electricity demand and network planning. | - All parties to continue coordination and participate in workshop on 21 May; align development plans with energy infrastructure constraints.

## 05_Risk Register
Stakeholder Risk Register
Risk ID | Risk | Linked Stakeholder | Cause | Likelihood | Impact | Overall Rating | Early Warning Indicator | Risk Response | Escalation Plan | Risk Owner | Target Closure | Status | Source / Rationale
R-01 | Pipeline buffer constraints reduce developable land | MoE / Aramco / Committee No.85 | Pipeline alignment and title deed affected lands not fully confirmed | High | High | Critical | MoE cannot confirm permitted uses or affected lands | Secure pipeline GIS and Committee No.85 input early | RCRC to integrate Committee No.85 representatives in meetings | Dry Utilities Lead | 2026-07-27 | Open | MoE Second MoM
R-02 | Land ownership/title deed gaps delay parcel reassignment | SPGA / MOJ / Ahmanh / momah and rcrc legal team | Inconsistent title deed lists and ownership datasets | High | High | Critical | Ownership data remains unconfirmed before land-use freeze | Make online workshop with momha and moj and amanh ; maintain assumptions register | Escalate unresolved ownership cases to RCRC | Land/Legal Lead | 2026-08-18 | Open | Riyadh Plan and MOMAH MoMs
R-03 | Ministry of Industry The area in the southe requirement redesign | MIM | Authorities may provide contradictory constraints | Medium | High | High | Late comments contradict approved direction | We keep those concerned constantly informed of all new developments in the project.Legal Response: The matter will be discussed with our Legal Team. The Ministry of Industry resolution and the Royal Decree appointing the authority responsible for the East Riyadh Project (East Grant) will be submitted for legal review. | RCRC to act as central coordinator and decision authority | WSP PM | 2026-08-31 | Open | SEMP risk register
R-07 | Absence of decision-maker in meetings | All external stakeholders | Invitations may not include empowered focal points | Medium | Medium | Medium | Meetings end with no decisions or repeated requests | Request named focal point and decision authority before meeting | Reschedule or escalate through RCRC/Lubna | Stakeholder Lead | 2026-07-16 | Open | SEMP stakeholder management principles
R-04 | MEWA DATA MUST HAVE | MEWA | New urgent stakeholder requests raised late | Medium | High | High | No response to agenda/data request within 5 working days | Prepare concise agenda and targeted questions; propose early Technical meeting | Escalate through RCRC if no focal point by target date | Environment / Urban Planning Lead | 2026-08-12 | Open | Client email request; SEMP register
R-05 | Meeting language/protocol issue delays MoE coordination | MoE / RCRC / WSP | MoE requested Arabic meetings and structured Excel questions | Medium | High | Medium | Materials shared only in English or without Excel questions | Prepare concise agenda and targeted questions; propose early Technical meeting | Escalate through RCRC if no focal point by target date | Stakeholder Lead | 2026-07-20 | Open | MoE MoM 11-May
R-05 | Delay in getting inputs from authorities (Ministry of Energy) | Moe |  | Medium | Medium | Medium |  | Regular follow-ups with relevant authorities and clear documentation of assumptions in project reporting. | Escalate it to RCRC after follow up with moe
R-06 | Action items remain open | All stakeholders | MoMs have several blank due dates/owners | High | Medium | Medium | Actions stay in 'open - verify status' for over 10 working days | Create weekly action closure tracker and assign owners | Escalate overdue actions in weekly RCRC meeting | Stakeholder Lead | 2026-07-24 | Open | Previous meetings tracker
R-08 | Missing Ministry of Industry data may affect the work, which is continuing based on assumptions until the required data is received. | Ministry of Industry and Mineral Resources | Coordination with the Ministry has not taken place due to the Council of Ministers decision and the Royal Decree. | High | High | Critical | Required Ministry data remains unavailable while the work continues based on assumptions. | Continue the work using documented assumptions until the required data is received from the Ministry of Industry. | Critical issue requiring management attention and Ministry coordination. |  |  | Open | Council of Ministers decision and Royal Decree; required Ministry data is still pending.

## 06_Detailed Question Bank
Entity / Stakeholder Name | S.no | Question | Responses | Date of response | Data Type | Why It Matters | Required Input | Question Importance Classification: Must-have / Nice-to-have | DMO
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 1 | What mandatory buffer or setback distances are required between Project East Grant and the Royal Reserve boundary? | Min 5km buffer from Reserve boundary. Larger buffers required for activities with significant environmental impacts, subject to IARDA approval. | 2026-07-23 |  | To define clear planning limits and avoid incompatible development near the Reserve. | Official buffer distances, setback rules, no-build zones, and reserve interface requirements. | Must have
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 2 | Are buffer widths dependent on habitat type, topography, proximity to wadis, or wildlife corridors? | Yes. Buffer widths vary by habitat sensitivity, topography, wadi proximity & wildlife corridors. Special attention to wadis and catchment areas required. | 2026-07-23 |  | To ensure buffers respond to actual environmental sensitivity rather than applying a single fixed distance. | Buffer methodology, sensitivity criteria, habitat-based requirements, and GIS layers. | Nice to have
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 3 | Are graduated buffers expected, such as no-build zones, low-impact zones, and managed landscape zones? | Yes. Graduated approach encouraged: no-build zones near sensitive habitats → low-impact zones → managed-use zones. Extent depends on site conditions. | 2026-07-23 |  | To guide land use intensity and define appropriate transition areas near the Reserve. | Buffer zoning hierarchy, permitted uses by zone, and edge management principles.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 4 | Should buffers be designed as ecological buffers, visual buffers, or multi-functional green infrastructure? | Primarily ecological buffers to protect habitats & wildlife. Visual/multifunctional features allowed if they support conservation objectives. | 2026-07-23 |  | To align buffer design with conservation, landscape, and development objectives. | Buffer design guidance, native habitat restoration requirements, visual screening standards, and green infrastructure expectations.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 5 | Which activities are permitted, restricted, or prohibited within buffer areas? | Permitted: conservation, habitat restoration, research, education, sustainable eco-tourism. Restricted/prohibited: activities with significant or long-term impacts. | 2026-07-23 |  | To confirm whether temporary, low-intensity, recreational, landscape, or service-related uses can be accommodated. | List of permitted/prohibited activities, temporary-use rules, and restrictions on permanent built uses.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 6 | Are service corridors or buried utilities permitted within buffers if surface conditions are restored? | Allowed where no alternatives exist, avoiding sensitive habitats & wadis. Requires environmental studies, IARDA approval, full restoration & monitoring. | 2026-07-23 |  | To understand whether infrastructure can cross or be located within sensitive edge areas. | Utility corridor rules, reinstatement requirements, access limitations, and approval conditions.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 7 | Are any wadis or drainage lines within the project site hydrologically connected to wadi systems within the Royal Reserve | Hydrological assessment required. Most wadis originate from Al Urumah Plateau draining to Rawdhat Khuraim. Any connectivity must be identified in planning. | 2026-07-23 |  | To understand whether site drainage may affect reserve hydrology and ecological systems | Confirmation of surface and subsurface hydrological connections, wadi linkage maps, and drainage data.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 8 | If connections exist, which onsite wadis drain toward or originate from reserve wadis, and are these connections episodic or perennial? | GIS data to be provided by IARDA. | 2026-07-23 |  | To distinguish storm-driven flows from permanent or recurring ecological/hydrological connections. | Specific wadi names/locations, flow direction, flow frequency, and seasonal behavior.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 9 | Are there mapped catchments or drainage studies used by the Authority that identify cross-boundary wadi linkages? | GIS data to be provided by IARDA. | 2026-07-23 |  | To align PEG hydrology assumptions with the Reserve Authority’s official evidence base. | Catchment maps, drainage studies, hydrological models, and approved GIS datasets.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 10 | Does the Authority consider any wadi features within the project site to function as ecological movement pathways connected to reserve wadis? | Yes, wadis function as ecological movement pathways. GIS data to elaborate. | 2026-07-23 |  | To identify whether wadis should be treated as ecological corridors, not only drainage features. | Ecological corridor mapping, movement pathway assessment, and priority wadi corridors
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 11 | Is maintaining wadi continuity under roads considered essential where connectivity to the Reserve exists? | Yes, essential. Road/infrastructure design must preserve natural water flows, sediment transport & ecological connectivity through appropriate crossings. | 2026-07-23 |  | To guide road crossings, culverts, bridges, and blue-green infrastructure design. | Design requirements for crossings, culvert/bridge standards, and continuity protection measures.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 12 | Is physical continuity of wadi features required, or is functional mitigation such as habitat enhancement elsewhere acceptable? | Physical continuity required. No habitat enhancement elsewhere accepted as substitute. Natural hydrological & ecological functions must be maintained. | 2026-07-23 |  | To understand whether impacts must be avoided directly or can be mitigated through enhancement measures. | Avoidance requirements, mitigation hierarchy, acceptable compensation measures, and approval criteria.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 13 | What priority habitats, biodiversity areas, or ecological corridors associated with the Reserve should be considered in PEG planning? | All habitats contributing to Reserve connectivity: wadis, catchment areas, wildlife corridors, restoration areas & species conservation habitats. | 2026-07-23 |  | To protect ecological connectivity and avoid impacts on sensitive habitats or species movement. | Habitat maps, biodiversity layers, ecological corridor data, sensitive zones, and species movement routes.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 14 | Does the Authority have records of small mammals, reptiles, or other fauna that may move outside the Reserve boundary via wadis or landscape features? | Yes, IARDA maintains biodiversity records. Additional field surveys required during planning phase to identify species & movement patterns. | 2026-07-23 |  | To understand whether PEG may support species movement or occasional fauna spill-over from the Reserve. | Species records, wildlife monitoring data, observation reports, and movement patterns.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 15 | Does the Authority consider the project site a secondary habitat, movement corridor, or occasional spill-over area for reserve fauna? | Site may function as secondary habitat & wildlife corridor. Extent to be confirmed through ecological surveys; design must maintain connectivity. | 2026-07-23 |  | To determine the ecological role of PEG in relation to the Reserve. | Authority assessment, species sensitivity data, corridor classification, and habitat use evidence.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 16 | What seasonal restrictions are relevant to this landscape, such as breeding periods or sensitive wildlife seasons? | Based on planning-phase surveys. Consider breeding, nesting & migration periods. Activities may be limited during sensitive periods. | 2026-07-23 |  | To inform construction timing, survey requirements, and activity restrictions. | Seasonal restriction periods, breeding calendars, survey windows, and construction control requirements.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 17 | What key considerations should guide the landscape and vegetation strategy, especially within wadis? | Strategy required with IARDA approval. Prioritize native habitats, ecological connectivity & natural hydrology. Use native species; avoid invasives. | 2026-07-23 |  | To clarify whether wadi enhancement planting is encouraged or whether wadis should remain largely natural. | Native planting guidance, wadi restoration approach, prohibited species, and vegetation management requirements.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 18 | Are dark-sky lighting standards required across the full project site or only near reserve-facing edges and wadi corridors? | Required in buffer areas, reserve-facing boundaries, wadis, catchment areas & wildlife corridors. Minimize light spill, glare & skyglow. | 2026-07-23 |  | To manage light impacts on wildlife while allowing practical urban lighting design. | Lighting standards, spatial application zones, lux limits, curfew requirements, and sensitive-area controls.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 19 | Can stronger construction controls offset lighter operational controls, or vice versa? | No trade-offs allowed. Construction and operational controls must be applied independently; stronger controls in one phase don't offset the other. | 2026-07-23 |  | To understand the acceptable balance between construction mitigation and long-term operational management. | Construction management requirements, operational controls, monitoring obligations, and mitigation flexibility.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 20 | Could the project attract pest or feral species or increase pest pressure along the Reserve perimeter? | Yes, risk exists. Planning studies must assess and identify prevention measures. Biosecurity & invasive species management plan required with IARDA approval. | 2026-07-23 |  | To avoid creating unintended ecological risks near the Reserve boundary. | Pest management guidance, reserve observations, risk factors, and control measures.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 21 | How should Project East Grant align with the Reserve’s strategic pillars, including protected nature, ecotourism, community engagement, and effective management? | Detailed ecological, hydrological & visual impact assessments required. Designs must protect sensitive areas, maintain connectivity & minimize disturbance. | 2026-07-23 |  | To ensure PEG supports the Reserve’s long-term strategic direction rather than creating conflicting development outcomes. | Strategic plan, pillar-specific objectives, planning principles, and alignment requirements.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 22 | Are there existing or planned Reserve management zones that may influence PEG’s future structure plan? | Yes, integration required. Coordinate visitor management, research programs & conservation activities. Potential for shared facilities in buffer zones. | 2026-07-23 |  | To ensure the masterplan aligns with the Reserve’s conservation and management direction. | Reserve management plan, zoning layers, conservation areas, and future expansion or protection priorities.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 23 | What type of ecotourism activities are planned within the Reserve, and what is the expected future visitor profile? | Joint technical reviews. Formal annual review with IARDA recommended; informal coordination as needed. Document all agreements. | 2026-07-23 |  | To understand whether PEG should plan for complementary visitor-support functions, mobility links, or hospitality uses. | Tourism strategy, activity types, visitor profiles, seasonal patterns, and target users.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 24 | What are the projected visitor numbers for the Reserve in the short, medium, and long term? | Graduated response required: no-build zones near sensitive areas, low-impact transitional zones, managed zones further out. Details per site assessment. | 2026-07-23 |  | To assess future demand on access, mobility, public realm, hospitality, parking, and visitor services around PEG. | Visitor forecasts, annual targets, peak demand assumptions, and seasonal variation.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 25 | Will there be designated gateways, access points, or visitor arrival corridors that may influence movement patterns around PEG? | Visual impact assessment required. Buildings/infrastructure should be designed to blend with landscape; minimize visibility from Reserve. | 2026-07-23 |  | To coordinate future access, road hierarchy, pedestrian/cycling links, and traffic assumptions. | Gateway locations, access strategy, transport corridors, visitor circulation plans, and parking requirements.
Imam Abdulaziz bin Muhammad Royal Reserve Authority | 26 | What coordination, approval, and data-sharing process should PEG follow with the Reserve Authority during future planning stages? | Refer to attached 'Project Implementation Guidelines for Royal Reserve' document for detailed requirements & standards. | 2026-07-23 |  | To clarify governance, avoid approval delays, and ensure Reserve requirements are embedded in the structure plan and masterplan update | Focal points, review process, approval pathway, required datasets, timelines, and coordination protocol.
MEWA | 1 | What is the status of Al Wasie Reserve and what protection requirements apply within or near the project area? | not received |  |  | To define protected land, restrictions, and buffers influencing development | Confirmed boundary, status, protection regulations, buffer requirements |  | DMO requires
MEWA | 2 | 2.What hydrology challenges affect the site? | not received |  |  | To understand flood risk and land suitability | Wadis, drainage paths, flood-prone areas, protection requirements |  | DMO requires
MEWA | 3 | What groundwater-related constraints affect development, and what is the status and permitted use of existing wells? | not received |  |  | To identify groundwater constraints and regulatory limitations | Well locations, status, abstraction limits, protection zones, future well plans |  | DMO requires
MEWA | 4 | What flora and fauna monitoring data is available for the site and surrounding areas? | not received |  |  | To assess ecological sensitivity and conservation requirements | Biodiversity surveys, protected species data, habitat mapping |  | DMO requires
MEWA | 5 | What geotechnical constraints related to wadis, escarpments, or mining areas should be considered? | not received |  |  | To ensure safe and suitable land development | Soil conditions, slope stability, mining zones, engineering constraints |  | DMO requires
MEWA | 6 | Are there any contamination, noise, or waste-related constraints that may impact development? | not received |  |  | To identify environmental risks affecting land use | Contaminated sites, waste facilities, noise sources, mitigation requirements |  | DMO requires
MEWA | 8 | Are there relevant programs or delivery mechanisms supporting infrastructure development? | Not yet received from MEWA. WSP included the data received from the RCRC, including the NWC report, which includes relevant information . Also we sent an email to RCRC with further details on the expected time of impleemntation of water assets. We still need confirmation from MEWA on the latest information regarding these assets and the strategy for the site. |  |  | To understand implementation and funding pathways | Programs, responsibilities, funding sources, delivery plans |  | DMO requires
MEWA | 9 | How should Project East Grant align with water resource management, environmental protection, and sustainability frameworks? | not received |  |  | To ensure compliance with national policies and achieve long-term resilience | Relevant frameworks, regulatory requirements, sustainability targets, alignment expectations |  | DMO requires
MEWA | 10 | Can MEWA verify and confirm the proposed KPIs for the future masterplan? | not received |  |  | To validate performance metrics and ensure alignment with MEWA priorities | KPI validation, target benchmarks, performance indicators, monitoring requirements |  | DMO requires
MEWA | 11 | What is MEWA’s strategy for TSE (treated sewage effluent) utilization, including centralized vs. decentralized treatment approaches? Are there any constraints or concerns regarding the proposed waste treatment facility within the site? | Not yet received from MEWA. We still need confirmation from MEWA on the latest information regarding these assets and the strategy for the site. |  |  | To confirm irrigation sustainability strategy and assess implications on infrastructure planning and development phasing | TSE strategy, treatment approach (centralized/decentralized), reuse requirements, constraints on waste treatment facility location and operations |  | DMO requires
MEWA | 12 | What is the timeline and priority for NWC water and wastewater assets, and has the referenced phasing been validated? | Not yet received from MEWA. We still need confirmation from MEWA on the latest information regarding these assets and the strategy for the site. | [5 empty] | DMO requires
MEWA | 13 | What is the status, location, and protection requirement of existing wells, and are there any future wells planned within or near the site? | not received | [5 empty] | DMO requires
MEWA | 14 | What groundwater use is permitted for irrigation, including restrictions, limitations, and allowable abstraction rates? | not received | [5 empty] | DMO requires
MEWA | 15 | What existing or planned utilities serve the site, including potable water, wastewater, irrigation, or treated sewage effluent (TSE)? | Not received yet. WSP has included the data received from the RCRC, including the NWC report, which contains the proposed sewage and potable water network assets. However, the MEWA to share the available information a related to this site to confirm. | [5 empty] | DMO requires
MEWA | 16 | Are there any strategic transmission lines from the Eastern Region crossing the site, and how can conflicts with future development be avoided? | not received | [5 empty] | DMO requires
Ministry of Energy | 1 | What existing energy infrastructure currently serves or crosses Project East Grant? | not received |  |  | To establish the confirmed infrastructure baseline and identify fixed planning constraints. | GIS layers, asset locations, ownership, operational status, and corridor alignments.
Ministry of Energy | 2 | What are the confirmed alignment, protection requirements, and exclusion zone widths for the Saudi Aramco pipeline? | not received |  |  | To define fixed infrastructure constraints and avoid conflict with land use, roads, and parcels. | Official pipeline alignment, exclusion zone width, setback requirements, permitted/prohibited activities.
Ministry of Energy | 3 | What protection requirements apply around power transmission corridors and substations? | not received |  |  | To define developable areas and safety constraints. | Setback rules, safety standards, clearance requirements, and access requirements.
Ministry of Energy | 4 | Are any future energy corridors or strategic projects required to be safeguarded within or near Project east grant? | not received |  |  | To avoid conflict with future infrastructure and prevent redesign. | Future corridor plans, expansion requirements, and safeguarding guidance.
Ministry of Energy | 5 | Are road crossings, utility crossings, or development interfaces permitted within the Aramco pipeline corridor? | not received |  |  | To understand whether the corridor can be integrated or must be fully avoided. | Crossing conditions, technical protection measures, approval process, and maintenance access requirements.
Ministry of Energy | 6 | What land uses are permitted, restricted, or prohibited within infrastructure buffers? | not received |  |  | To guide land use allocation in constrained areas. | Compatible land use guidance, activity restrictions, and development control rules.
Ministry of Energy | 7 | Can low-impact uses such as open space, landscaping, parking, or service roads be located within buffer areas? | not received |  |  | To optimize land use while respecting safety requirements. | Permitted use list, design conditions, and operational restrictions.
Ministry of Energy | 8 | Are temporary construction activities allowed near pipeline or power corridors? | not received |  |  | To inform phasing, construction logistics, and risk management. | Construction control requirements, temporary access rules, and permit conditions.
Ministry of Energy | 9 | What demand assumptions should Project east grant adopt for future electricity servicing? | not received |  |  | To align future development with realistic capacity planning. | Load assumptions, demand criteria, capacity guidance, and planning standards.
Ministry of Energy | 10 | Are new substations, grid reinforcement, or transmission upgrades expected to serve Project east grant? | not received |  |  | To identify land requirements and delivery dependencies. | Planned upgrades, substation requirements, reinforcement strategy, and phasing assumptions.
Ministry of Energy | 11 | What is the preferred servicing approach for future development areas? | not received |  |  | To shape the infrastructure strategy and sequencing | Network hierarchy, servicing principles, delivery approach, and technical requirements.
Ministry of Energy | 12 | Renewable and sustainability road maps and targets to be adopted. | not received |  |  | To align PEG with national frameworks. | Renewable Energy targets/constraints, RE road maps, focal points (departments/authorities) for further coordination, applicable guidelines, Etc
Ministry of Energy | 13 | What coordination and approval pathway should Project east grant To follow with the Ministry of Energy and related entities? | not received |  |  | To avoid delays and ensure correct engagement sequence. | Focal points, review process, approval pathway, and timelines.
Ministry of Energy | 14 | What datasets should be formally provided to support the masterplan update? | not received |  |  | To ensure all planning assumptions are evidence-based. | GIS data, technical standards, asset information, future plans, and restrictions.
Ministry of Energy | 15 | Are additional technical studies required before confirming land use options? | not received |  |  | To strengthen the masterplan and reduce implementation risk | Required studies, scope, responsible entities, and timing.
Ministry of Energy | 16 | What are the key risks the project should address early from an energy infrastructure perspective? | not received |  |  | To manage delivery, safety, and feasibility risks. | Risk register inputs, mitigation requirements, and critical coordination issues.
Ministry of Energy | 17 | Can the red pipeline exclusion zone be recognised in the Structure Plan as a controlled, non-developable open area, without public access? | not received |  |  | This clarifies whether the land can contribute to the spatial/open-space framework without conflicting with safety restrictions. | Confirmation of acceptable terminology, access restrictions, and any prohibited landscape or public-realm treatments.
Ministry of Energy | 18 | Is there any policy or technical intention to reduce, rationalise, or reclassify the current pipeline protection zone widths over time? | not received |  |  | The current red/orange/yellow buffer widths significantly affect land suitability and the overall structure plan. | Confirmation whether the 500m / 400m / 350m zones are fixed, provisional, or subject to technical review.
Ministry of Energy | 19 | What technical criteria would need to be met to consider a narrower protection zone, based on global precedents or local risk standards? | not received |  |  | This turns the question from “can we reduce it?” into a professional risk-based discussion. | Risk criteria, pipeline pressure/diameter/depth data, land-use sensitivity rules, emergency access standards, and approval requirements.
Ministry of Energy | 20 | Since RCRC is responsible for determining suitable land uses across the three zones, what safety and operational constraints should MoE / Saudi Aramco provide to guide RCRC’s land-use decision? | not received |  |  | This aligns with the joint committee outcome and avoids implying that MoE is the land-use approving authority. | Permitted / restricted / prohibited activities, maintenance access, crossing controls, emergency-response requirements.
Ministry of Energy | 21 | Are passive landscape, ecological corridors, drainage corridors, service roads, or restricted-access green buffers acceptable within the pipeline protection zones? | not received |  |  | This helps convert constrained land into planned, useful, but safe infrastructure landscape. | List of compatible uses, design conditions, fencing/access requirements, and maintenance controls.
Ministry of Energy | 22 | Is there an existing intention to convert the high-voltage overhead transmission lines within Project East Grant to underground cables or reroute them? If yes, when and under which programme? | not received |  |  | The overhead lines affect visual quality, land efficiency, development flexibility, and phasing. | Programme status, timeframe, responsible entity, funding responsibility, and interim planning assumptions
RIPC | 1 | What existing or planned infrastructure projects within or around Project East Grant should be reflected in the Structure Plan? | not received |  |  | To avoid conflicts with current or future infrastructure works. | Confirmed project list, GIS layers, corridors, and delivery timelines. |  | DMO requires
RIPC | 2 | What protected corridors, rights-of-way, utility reservations, or construction restrictions must be safeguarded in the master plan? | not received |  |  | To ensure compliance and avoid planning over restricted infrastructure areas. | ROW requirements, buffer zones, restrictions, and applicable standards. |  | DMO requires
RIPC | 3 | What RIPC standards, guidelines, or regulatory requirements should guide infrastructure planning for Project East Grant? | not received |  |  | To align the project with RIPC’s regulatory and technical expectations from the outset. | Relevant standards, design guidelines, submission requirements, and review criteria |  | DMO requires
RIPC | 4 | What are the key infrastructure conflicts or risks RIPC expects the project team to address early? | not received |  |  | To reduce redesign, delays, and implementation risks. | List of known conflicts, critical interfaces, and recommended mitigation approach. |  | DMO requires
RIPC | 5 | What is the required process for coordinating with service providers and resolving cross-entity infrastructure issues? | not received |  |  | To clarify roles, responsibilities, escalation routes, and decision-making. | Coordination process, priority entities, escalation path, and responsible focal points. |  | DMO requires
RIPC | 6 | What approvals, permits, no-objection requirements, or review checkpoints are required before finalising the Structure Plan? | not received |  |  | To ensure the planning process is aligned with RIPC’s approval pathway. | Approval sequence, submission package, review stages, and expected outputs. |  | DMO requires
RIPC | 7 | How should infrastructure delivery and project phasing be aligned with RIPC’s planned programmes and citywide infrastructure priorities? | not received |  |  | To ensure the project is deliverable and phased realistically. | Infrastructure programme, dependencies, phasing assumptions, and priority projects. |  | DMO requires
Ministry of Transport & Logistics Services | 1 | What are the confirmed alignment, capacity, and upgrade plans for Rumah, Dammam, and Al Khurais Roads? | Response received |  |  | To define fixed transport constraints, avoid congestion bottlenecks, and plan for redundancy and freight segregation. | GIS layers, official road alignment, capacity studies, planned upgrades, and phasing schedules.
Ministry of Transport & Logistics Services | 2 | Is re‑alignment of the proposed railway expansion line (Riyadh – Dammam line) possible if designated for freight, or can the current alignment be adapted to leverage passenger connectivity (e.g., integration with Q‑Express) | Response received |  |  | To determine whether the corridor should be safeguarded for freight logistics or optimized for passenger services. This decision directly affects site accessibility, multimodal integration, and long‑term phasing of transport infrastructure. | Official guidance on railway alignment flexibility, freight vs. passenger designation, safeguarding requirements, way‑leave approvals, and integration plans with Q‑Express and wider Riyadh mobility network.
Ministry of Transport & Logistics Services | 3 | Can the 3rd Ring road be extended to the site to provide opportunities for further connection to Project Grant site? | Response received |  |  | Extending the 3rd ring road would provides stronger vehicular and multimodal access, reducing reliance on Dammam road. | Official guidance on 3rd ring road alignment feasibility, integration with existing masterplans, right‑of‑way availability, phasing timelines, integration with existing corridors
Ministry of Transport & Logistics Services | 4 | Are any further future mobility corridors or strategic projects required to be safeguarded within or near Project east grant? | Response received |  |  | To avoid conflict with future infrastructure and prevent redesign | Future corridor plans, expansion requirements, and safeguarding guidance.
MOMAH | 1 | Is Project East Grant within MOMAH’s jurisdiction, and what parts of the site are owned, managed, or overseen by MOMAH? | Response received |  |  | To clarify the Ministry’s role, land responsibility, and the applicable planning authority. | Ownership records, jurisdiction boundaries, custodianship responsibilities, and land administration status.
MOMAH | 2 | What approved plans, designated areas, or previous planning decisions already apply within the site? | not received |  |  | To understand the existing planning baseline and avoid conflict with prior approvals or designations. | Approved plans, zoning maps, designated land uses, previous approvals, and planning history
MOMAH | 3 | Are there any adjacent MOMAH-led or municipally approved projects outside the site that Project East Grant should consider? | not received |  |  | To ensure the masterplan responds to surrounding growth, interface conditions, and future dependencies. | Pipeline projects, adjacent development plans, reserved lands, and future road or service corridors.
MOMAH | 4 | What land uses, densities, heights, and plot controls are permitted within the site? | not received |  |  | To define development capacity and ensure compliance with planning regulations. | Zoning regulations, development control parameters, density ranges, height limits, and plot controls.
MOMAH | 5 | What urban design, public realm, and street design standards should guide the masterplan? | not received |  |  | To guide urban form, street hierarchy, public realm quality, and built-form outcomes | Urban design guidelines, street standards, public realm requirements, code manuals, and reference sections.
MOMAH | 6 | Are there specific requirements for community facilities, open space, or housing provision that should be reflected in the plan? | not received |  |  | To align the masterplan with municipal and housing objectives and ensure adequate service provision. | Community facility standards, open space requirements, housing standards, and service benchmarks.
MOMAH | 7 | If MOMAH retains responsibility for parts of the site, how will land, public realm, and infrastructure operation and management be handled? If not, which authority would assume this responsibility? | not received |  |  | To clarify long-term governance, operation, maintenance, and handover responsibilities. | Operation and maintenance model, transfer arrangements, responsible entities, and handover conditions.
MOMAH | 8 | How should infrastructure planning be coordinated with MOMAH, and with which infrastructure authorities should alignment be established? | not received |  |  | To ensure alignment between land use planning, municipal service delivery, and implementation feasibility. | Infrastructure standards, service coverage requirements, thresholds, coordination inputs, and authority interfaces.
MOMAH | 9 | Is there a required phasing framework for approved development areas? | not received |  |  | To enable viable phasing strategies and avoid delivery or occupancy constraints. | Phasing guidance, sequencing rules, infrastructure trigger requirements, and milestone conditions.
MOMAH | 10 | What is the approval pathway for Project East Grant, and which submissions, reviews, and endorsements are required from MOMAH? | not received |  |  | To define approval stages, responsibilities, and realistic programme timelines. | Approval flowcharts, authority roles, submission requirements, review timelines, and dependencies.
MOMAH | 11 | What inputs, documents, and compliance confirmations are required from MOMAH for the masterplan update and statutory endorsement? | not received |  |  | To ensure the masterplan is aligned, approvable, and ready for statutory submission. | Required drawings, reports, policy confirmations, compliance statements, and endorsement inputs.
MOMAH | 12 | Are there any specific implementation conditions, municipal commitments, or statutory reservations that should shape the final masterplan? | not received |  |  | To identify any hidden constraints or commitments that may affect delivery, coordination, or land availability. | Reserved land requirements, implementation conditions, municipal commitments, and special approval requirements.
Wadi Al-Sulai Project Team | 1 | Is it Possible to Divert Wadi alignments in some scenarios? متى يلزم تحويل مسارات الأودية في بعض الحالات وما التحديات التي واجهتها الأمانة؟ | Response received | 2026-06-09 | Clarified in meeting
Wadi Al-Sulai Project Team | 2 | What is the Wadi Al Sulai buffer from the slope crest, does it follow the 25m standard used in Wadi Hanifah, or is it determined by flooding depth? ما هو نطاق الحمى في وادي السلي من حافة الوادي،و هل يتم تحديدها من خلال عمق الفيضان؟ | Response received | 2026-06-09 | Clarified in meeting
Wadi Al-Sulai Project Team | 3 | How are crossings and constraints managed (roads, culverts, utilities) to keep drainage continuity? كيف تتم إدارة التقاطعات والقيود (الطرق، والعبارات، والمرافق) للحفاظ على استمرارية الصرف؟ | Response received | 2026-06-09 | Clarified in meeting
Wadi Al-Sulai Project Team | 4 | What measures were considered to protect biodiversity and maintain sustainable ecological linkages between habitats across different areas? ما هي التدابير التي تم النظر فيها لحماية التنوع البيولوجي والحفاظ على الروابط البيئية المستدامة | Response received
Wadi Al-Sulai Project Team | 5 | Who are the involved entities and what is the decision pathway (committee, approvals, escalation)? من هي الجهات المعنية وما هو مسار اتخاذ القرار | Response received |  |  | East grant needs clear governance to reduce delays and avoid fragmented decisions. يحتاج مشروع منح شرق إلى حوكمة واضحة للحد من التأخيرات وتجنب القرارات المجزأة. | Governance chart, committee structure, escalation matrix, authority list. الهيكل الحوكمي و ادوار الجهات المهنية
Wadi Al-Sulai Project Team | 6 | How are encroachments identified, recorded, and classified (type, severity, flood depth, buffers, etc.)? كيف يتم تحديد التعديات وتسجيلها وتصنيفها (عمق الفيضان، والمناطق العازلة، وما إلى ذلك)؟ | Response received |  |  | Enables a defensible case registry and prioritisation for large volumes. لتعريف قطع الأراضي المنتهكة للأودية التي تتطلب نزعها و نقلها | Surveying method of encroachments. طريقة حصر القطع المتقاطعة مع الأودية.
Wadi Al-Sulai Project Team | 7 | What is the end-to-end workflow for removals (notice → deadline → enforcement → closure)? ما هي آلية العمل الكاملة لعمليات النزع (الإشعار، الموعد النهائي للإخلاء، التنفيذ)؟ | Response received |  |  | Provides a practical operation procedure that East Grant can adapt for consistent lawful implementation. يوفر إجراءً عملياً يمكن لمشروع منح شرق تكييفه من أجل التنفيذ القانوني المتسق. | Process operation, notice templates, timeframes, closure criteria. عملية التشغيل، الأطر الزمنية، حتى إتمام عملية النزع.
Wadi Al-Sulai Project Team | 8 | How are ownership claims handled when overlapping the corridor (permits, titles, informal uses)? كيف يتم التعامل مع النوعيات المختلفة لأوضاع الملكية للأراضي أو المنشئات عند تداخل الممر (التصاريح، الصكوك، التعديات)؟ | Response received |  |  | Reduces disputes and clarifies when restriction vs removal is legally feasible. يقلل من النزاعات ويوضح متى يكون التقييد مقابل الإزالة ممكناً من الناحية القانونية. | Policy approach, dispute scenarios, coordination points with legal/land entities. سياسات التعامل المختلفة، سيناريوهات النزاع، نقاط التنسيق مع الكيانات القانونية/الأراضي.
Wadi Al-Sulai Project Team | 9 | What sequencing logic was applied (protect corridor first, infrastructure first, then activation)? ما هو منطق التسلسل الذي تم تطبيقه (حماية الممر أولاً، ثم البنية التحتية أولاً، ثم التفعيل)؟ | Response received |  |  | Informs East Grant phasing triggers and prevents rework or re-occupation. يُبلغ هذا النظام منطقة مشروع منح شرق إ بمراحل التنفيذ ويمنع إعادة العمل أو إعادة شغل الموقع | Phasing plan, triggers between phases, lessons learned on delays. خطة التنفيذ و مرحاله، والمحفزات بين المراحل، والدروس المستفادة من التأخيرات.
Wadi Al-Sulai Project Team | 10 | Who is responsible for O&M and preventing re-encroachment after delivery (monitoring, inspections, contracts)? من المسؤول عن التشغيل والصيانة ومنع التعدي مرة أخرى بعد التسليم (المراقبة، عمليات التفتيش، العقود)؟ | Response received |  |  | Long-term performance depends on clear ownership, funding, and enforcement. يعتمد الأداء على المدى الطويل على الملكية الواضحة والتمويل والتنفيذ. | O&M ownership model, monitoring regime, enforcement approach, KPIs (if any). هيكل التشغيل والصيانة، ونظام المراقبة، ونهج الإنفاذ.
Riyadh Municipality - General Directorate of Stormwater Networks | 1 | How the detention storage ponds works in VI-A section. Is it a combination of local runoff + diverted wadi flow. | Response received | 18/06/2026 | Clarified in meeting | The inlet mechanism from the wadi to the ponds is not described, making it unclear . such as - At what water level diversion starts. - how much flow is diverted, - whether diversion occurs only during floods of 100 yrs or also during minor events. | Details about how the proposed detention storage works. Any drawings regarding how this ponds works together as a system, series, cascaded.
Riyadh Municipality - General Directorate of Stormwater Networks | 2 | The report doesn't inform the ground water tables and infiltration capacity of soil. Is that VI-A catchment is suitable for ground water recharge and detention storage | Response received | 18/06/2026 | Clarified in meeting | Waterlogging observed during dry season site visits indicates limited soil infiltration capacity. A preliminary assessment is required to evaluate pond behaviour post-storm events. While pond storage may attenuate peak flows in the wadi, infiltration is likely to be slow, and evaporation effects should also be considered. | Any such study report for the region/soil investigation report.
Riyadh Municipality - General Directorate of Stormwater Networks | 3 | Why has no clear flood mitigation strategy been proposed for Wadis V3, V4, and V5, despite these channels being designed to convey very high peak discharges (up to 100 m³/s) for Wadi V4? | Response received | 18/06/2026 | Clarified in meeting | Report does not clearly articulate a flood mitigation philosophy beyond channel conveyance for V4. | Are any alternative mitigation strategies evaluated?
Riyadh Municipality - General Directorate of Stormwater Networks | 4 | While assessments are presented for both 10‑year and 100‑year return periods, the report does not clearly specify the governing design storm. Please confirm the final adopted storm event ( 100 yrs?)used for sizing the key drainage infrastructure.. | Response received | 18/06/2026 | Clarified in meeting | Drainage Systems are designed for certain storm Return Periods, bigger storm can cause infrastructure damage/ overtopping/ flooding | Please confirm
Riyadh Municipality - General Directorate of Stormwater Networks | 5 | Why the integration of Wadi V2 within the overall drainage network is not clearly described | Response received | 18/06/2026 | Clarified in meeting | Missing link
Riyadh Municipality - General Directorate of Stormwater Networks | 6 | What criteria need to be used for fixing the buffers for Wadi? | Response received | 18/06/2026 | Clarified in meeting | To establish the natural constraints for protecting wadis and go for a sustainable development. | Any policy documents/ references comprising the methodology for fixing the wadi buffers
Riyadh Municipality - General Directorate of Stormwater Networks | 7 | Any most recent update on Hydrology study covering entire PEG? | Response received | 18/06/2026 | Clarified in meeting | To update our baseline study | Any hydrology model files, documents and GIS layers
Riyadh Municipality - General Directorate of Stormwater Networks | 8 | Location of Existing storm water infrastructure (Culvert, Bridges, Rioadside drains etc.) and flood management system available in East Grant? | Not received the data as discussed in the meeting | 18/06/2026 | GIS Data | To understand the existing models and constraints | Any layers on Existing Storm Water drainage infrastructure
Riyadh Municipality - General Directorate of Stormwater Networks | 9 | Any past flood affected locations identified in PEG? | Not available | 18/06/2026 | Clarified in meeting | To validate the study which we have done as part of Baseline | Any layers on Existing Storm Water drainage infrastructure
Riyadh Municipality - General Directorate of Stormwater Networks | 10 | Requirement of Terrain Survey Data/ DEM | Data Receieved but it is too old and suitable for PEG study | 24/06/2026 | Point data in CAD | To integrate any ongoing study with project east grant reports | Terrain Survey Data/ DEM
Riyadh Municipality - General Directorate of Stormwater Networks | 11 | Requirement of High Resolution Photographs (if available) | Not available | 18/06/2026 |  | High Resolution photographs to understand the study area in more detail | High Resolution photography
Riyadh Municipality - General Directorate of Stormwater Networks | 12 | Requirement of Hydrology and Hydraulic model files | Response received | 24/06/2026 | Model files | To integrate the latest data with project east grant reports | Hydrology and Hydraulic models like, HEC-HMS, HEC-RAS 1D, Culvert Master, FlowMaster used for Amanah
Ministry of Industry and Mineral Resources | 1 | Request for information to understand the extent and implications of the mineral resources of current and future development, Information includes the following: • The extent of silica reserve areas and its effect for the project development • Constraints related to mining or protection requirements • Potential opportunities for industrial use • Mining plans for surface quarries and underground mines (existing and planned) • Mining depths • Current status of mines (active, inactive, or backfilled) |  |  |  | To undersatnd the future plans of mining development and current constraints for project devemlopment. | Ministry of Industry and Mineral Resources analysis of the project data against mining plans and their support to provide the required information in applicable formats (CAD DWG, PDF, GIS layer, etc…)

## 7New Questions Not Asked Before
Entity / Stakeholder Name | S.no | Question | Why It Matters | Question Importance Classification: Must-have / Nice-to-have

## Follow up status
Stakeholder Follow-up Status
Summary of the latest update, follow-up status, and next action for each stakeholder
Stakeholder | Latest Update / Current Status | Follow-up Status | Next Action
RCRC | The latest meeting concerned legal issues, and an invitation was sent for them to attend the meeting with the Ministry of Municipalities and Housing and Riyadh Municipality. | No follow-up currently required | —
Riyadh Plan | The centers maps and other useful information were received, and the received maps were aligned with the project maps. | No follow-up currently required | —
Ministry of Energy | The latest meeting was held at the end of July, and it was agreed to hold regular coordination meetings. The Ministry's Content Percentage was also updated. | Follow up later | All updates will be shared with them during the third coordination meeting after Stage 3 approval.
Riyadh Municipality – Planning Department | A meeting was held with them at the end of July in the presence of the Ministry of Municipalities and Housing. Several queries were raised, but no responses have been received yet. | Follow-up completed ON 24 AUG | Complete the data review and identify any gaps or further coordination requirements
Riyadh Municipality – Wadis Department | The requested files were received, but they are incomplete. They were contacted on 16 August to provide the missing information. | Awaiting response | Wait for their response and follow up as needed.
MEWA – Ministry of Environment, Water and Agriculture | Further coordination is required to obtain the requested information. | Follow-up required | Coordinate with the Data Management/Exchange Office (DMO).
RIPC | Update / Notes: The requested data was received on 19 August and is currently being reviewed by the Wet & Dry Utilities team. | Under review – no follow-up required at this stage | Complete the data review and identify any gaps or further coordination requirements
Imam Abdulaziz bin Muhammad Royal Reserve Authority | Update / Notes: The requested data was received on 19 August and is currently being reviewed by the team. | Under review – no follow-up required at this stage | Complete the data review and identify any gaps or further coordination requirements
Ministry of Municipalities and Housing (MOMAH) | A meeting was held at the end of July in the presence of Riyadh Municipality. Several points were raised, but no responses have been received yet. | Follow-up completed ON 24 AUG | Complete the data review and identify any gaps or further coordination requirements
Ministry of Industry and Mineral Resources | They cannot currently be contacted despite the need for important information from the Ministry due to legal constraints. The matter has been recorded in the Risk Register. | On hold due to a legal constraint | Continue monitoring the matter through the Risk Register until the legal constraint is resolved.
SPGA | They were contacted at the end of July to clarify several points, but no response has been received yet. | Follow-up required | Follow up with them on 20 August.
Ministry of Justice | The requested files were received from the Ministry. | No follow-up currently required | —
Ministry of Transport and Logistics Services | The requested files were received. | No follow-up currently required | A second coordination meeting is required after Stage 3 approval.

## 07_Scenarios (hidden)
Post-Meeting Scenario Planning
Best-case, most-likely and worst-case outcomes are defined for high-priority Stage 4 stakeholder meetings.
Stakeholder / Cluster | Scenario | Expected Outcome | Data / Decisions Obtained | Impact on Stage 4 Programme | Next Step | Mitigation / Escalation
Riyadh Plan Team | Best-Case | Clear confirmation that the Stage 3 aligns with Riyadh Plan direction | Site role, centres hierarchy and transport logic | Reduces rework and provides defensible planning basis | Incorporate comments into structure plan | None required
Riyadh Plan Team | Most-Likely | General alignment with specific comments to refine | Comments on centres and network assumptions | Minor edits before structure plan freeze | Update design log | Track comments with RCRC
Riyadh Plan Team | Worst-Case | Riyadh Plan direction conflicts with current Stage 4 assumptions | No clear decision or preference | Major redesign risk | Escalate to RCRC leadership | Prepare options impact note
MoE / SEC / National Grid / Aramco | Best-Case | Pipeline, power and cost-review requirements confirmed | GIS layers, buffers, demand review route | Dry utility assumptions can be integrated early | Update constraints and cost model | Maintain three-week cadence
MoE / SEC / National Grid / Aramco | Most-Likely | MoE confirms review process but data remains partially open | Preliminary constraints and action list | Proceed with assumptions but flag risk | Submit formal RFI | Escalate overdue items
MoE / SEC / National Grid / Aramco | Worst-Case | No data or no permission to share Royal Orders/affected lands | No buffers or demand data | Cost/dry utility validation delayed | Escalate through RCRC and Committee No.85 | Use conservative buffers and assumptions
Riyadh Municipality - Stormwater / Wadi | Best-Case | HEC data and wadi buffer principles are confirmed | Models, culvert info, spot levels, buffer approach | 2D model and land-use freeze proceed on time | Update hydrology model and developable land map | No escalation
Riyadh Municipality - Stormwater / Wadi | Most-Likely | Partial data received; old data caveats remain | Some models/reports and limitations | Proceed with documented assumptions | Validate and request missing items | RCRC follow-up
Riyadh Municipality - Stormwater / Wadi | Worst-Case | No shareable data and no confirmed buffer approach | None or unusable data | High risk to structure plan and EIA | Escalate to Amanah senior sponsor | Use independent modelling and conservative buffers
MEWA / SIO | Best-Case | Environmental and water constraints confirmed | Environmental datasets and approval route | EIA scope becomes clearer | Integrate into EIA and structure plan | None
MEWA / SIO | Most-Likely | MEWA provides high-level direction only | Key requirements but limited data | Need additional RFI | Record assumptions and follow up | RCRC to request datasets
MEWA / SIO | Worst-Case | No focal point or conflicting environmental requirements | No formal input | EIA assumptions remain exposed | Escalate through RCRC | Document information gap and use baseline data
Royal Reserve Authority | Best-Case | Ecological corridors and reserve interface accepted | Reserve feedback and watershed considerations | Environmental framework strengthened | Integrate into plan and EIA | None
Royal Reserve Authority | Most-Likely | Feedback received but requires technical follow-up | Partial comments and queries | Minor schedule impact | Schedule focused follow-up | Track open queries
Royal Reserve Authority | Worst-Case | Reserve concerns reject proposed approach | No acceptance of ecological interface | Redesign near reserve edge | Escalate to RCRC environmental leadership | Prepare alternative buffer scenarios
MOMAH | Best-Case | MOMAH confirms land-use/housing alignment and Plot No.2 status | Policy comments, housing/future plan confirmation | Structure plan can proceed with clearer housing assumptions | Update land-use plan | None
MOMAH | Most-Likely | MOMAH requests internal review after meeting | Materials accepted for review | Potential delay to formal feedback | Provide written comments tracker | RCRC follow-up
MOMAH | Worst-Case | MOMAH identifies major conflict with approved plans or housing objectives | No clearance on Plot No.2 | Rework in land use and compensation approach | Escalate with RCRC | Prepare options for affected areas
RIPC | Best-Case | Service provider strategy and funding model inputs shared | KMZ verification, 5-year plan, funding mechanism | Infrastructure phasing and costing strengthened | Update infrastructure phasing | None
RIPC | Most-Likely | RIPC confirms direction but documents require approval | High-level guidance only | Proceed with assumptions until documents shared | Follow up approvals | RCRC to unlock documents
RIPC | Worst-Case | RIPC cannot share strategy or confirm service coverage | No useful input | Infrastructure phasing remains high-risk | Escalate via RCRC | Proceed with conservative assumptions
Ministry of Industry and Mineral Resources | Best-Case | Mineral reserve boundaries and restrictions confirmed | GIS layers and permitted/restricted land uses | Developable land map can be finalized | Update constraints and land-use plan | None
Ministry of Industry and Mineral Resources | Most-Likely | Ministry provides general direction and requests internal review | Initial comments and data request list | Minor schedule dependency | Formal RFI follow-up | RCRC follow-up if delayed
Ministry of Industry and Mineral Resources | Worst-Case | No data or unclear mineral reserve boundary | No decision on restrictions | Land suitability remains exposed | Escalate through RCRC | Use conservative buffer until confirmed
MOTLS / RGA / TGA / SAR | Best-Case | Transport corridors and ROW confirmed | Road alignments, mobility and logistics constraints | Movement network can be frozen | Update transport plan | None
MOTLS / RGA / TGA / SAR | Most-Likely | Comments received but some corridors still subject to future studies | Partial network feedback | Carry assumptions with caveats | Schedule follow-up | RCRC Mobility escalation
MOTLS / RGA / TGA / SAR | Worst-Case | Major transport changes or ROW conflicts emerge late | Conflicting alignments | Structure plan redesign risk | Escalate via RCRC Mobility | Prepare alternative network scenarios
SPGA / MOJ | Best-Case | Ownership and title deed gaps closed | Ownership data, legal status and affected lands | Parcel reassignment and land treatment can progress | Update legal and parcel registers | None
SPGA / MOJ | Most-Likely | Partial validation and remaining cases flagged | Partial data and disputed cases | Plan proceeds with exceptions log | Create unresolved cases list | Weekly RCRC legal follow-up
SPGA / MOJ | Worst-Case | Critical ownership data unavailable | No validated legal basis | Stage 4 land decisions exposed | Escalate to RCRC Legal | Use assumptions and defer final parcel decisions

## 08_Prioritization (hidden)
Stakeholder Prioritization Matrix
Scoring is based on influence, interest, dependency and decision sensitivity. Categories are formula-driven and can be revised by the project team.
Stakeholder / Cluster | Influence (1-5) | Interest (1-5) | Dependency (1-5) | Decision Sensitivity (1-5) | Total Score | Matrix Category | Engagement Priority | Rationale
RCRC | 5 | 5 | 5 | 5 | 20 | Manage Closely | Critical | Central coordinator and approval route
Riyadh Plan Team | 5 | 5 | 5 | 5 | 20 | Manage Closely | Critical | City-wide direction and strategic alignment
MoE / SEC / National Grid / Aramco | 5 | 5 | 5 | 5 | 20 | Manage Closely | Critical | Pipeline, power and dry utility constraints
Riyadh Municipality - Stormwater | 5 | 5 | 5 | 5 | 20 | Manage Closely | Critical | Hydrology data and 2D model dependency
Wadi Al-Sulai Project Team | 5 | 5 | 5 | 5 | 20 | Manage Closely | Critical | Wadi buffers and affected parcels
MEWA / SIO | 4 | 4 | 4 | 5 | 17 | Manage Closely | High | Environmental and water constraints
Royal Reserve Authority | 4 | 5 | 4 | 5 | 18 | Manage Closely | Critical | Ecological corridors and reserve interface
MOMAH | 5 | 4 | 4 | 5 | 18 | Manage Closely | Critical | Planning/housing policy and approved plan alignment
RIPC | 4 | 4 | 4 | 4 | 16 | Manage Closely | High | Infrastructure phasing and provider strategy
Ministry of Industry and Mineral Resources | 4 | 3 | 4 | 5 | 16 | Keep Satisfied | High | Mineral reserve / industrial constraints
MOTLS / RGA / TGA / SAR | 4 | 3 | 4 | 4 | 15 | Keep Satisfied | High | Transport corridors and ROW
SPGA | 5 | 3 | 5 | 5 | 18 | Keep Satisfied | Critical | State property ownership
Ministry of Justice | 5 | 3 | 5 | 5 | 18 | Keep Satisfied | Critical | Title deed and legal ownership validation
Utilities Cluster - Wet | 3 | 4 | 4 | 4 | 15 | Keep Informed | High | Wet utilities capacity and standards
Utilities Cluster - Digital | 3 | 3 | 3 | 3 | 12 | Monitor | Medium | Digital infrastructure corridors
PIF / Strategic Landowners | 3 | 3 | 3 | 4 | 13 | Monitor | Medium | Future vision for owned/influenced lands
Ministry of Interior / General Traffic | 4 | 2 | 3 | 4 | 13 | Keep Satisfied | Medium | Traffic/security/restricted land constraints
Ministry of Defense | 4 | 2 | 3 | 5 | 14 | Keep Satisfied | High | Non-developable defense land

## 09_Two-Week Plan (hidden)
Two-Week Priority Action Plan
Actions required immediately to move from Stage 2/3 follow-up into Stage 4 stakeholder engagement.
Action No. | Urgent Action | Owner | Target Date | Linked Stakeholder | Purpose | Output | Status | Escalation if Delayed
1 | Validate and agree Stage 4 stakeholder priority list with RCRC/Lubna | Stakeholder Lead | 2026-07-14 | RCRC | Lock meeting sequence | Approved stakeholder list | Planned | Escalate in weekly RCRC PM meeting
2 | Confirm focal points and decision-makers for MEWA and MIMR | RCRC / Stakeholder Lead | 2026-07-15 | MEWA / MIMR | Prepare urgent requested agendas | Confirmed invitees | Not Started | RCRC to nominate contacts
3 | Prepare concise agenda packs for MEWA and MIMR | Environment Lead / Urban Planning Lead | 2026-07-16 | MEWA / MIMR | Respond to client request | Two meeting agendas and question lists | Not Started | WSP PM review
4 | Update previous action tracker with confirmed status from each WSP lead | Stakeholder Lead | 2026-07-17 | All | Separate real open items from closed actions | Clean action tracker | Planned | Escalate missing statuses to discipline leads
5 | Prepare MoE/SEC/Aramco Stage 4 submission pack | Dry Utilities Lead | 2026-07-17 | MoE / SEC / Aramco | Enable 20-Jul coordination | Presentation + Excel questions | Planned | Escalate if Stage 3 outputs not approved
6 | Confirm Committee No.85 representatives in MoE meeting invite | RCRC / Stakeholder Lead | 2026-07-17 | MoE | Avoid duplication and align pipeline decisions | Updated invite list | Information Required | RCRC PM escalation
7 | Follow up Riyadh Municipality hydrology data promised within one month | Hydrology Lead | 2026-07-18 | Amanah Stormwater | Obtain HEC/model/survey data | Data request status | Open - verify status | Escalate to Amanah senior technical sponsor
8 | Prepare integrated constraints map for Stage 4 meetings | GIS Lead | 2026-07-19 | RCRC / All | Support all stakeholder discussions | Draft constraints map | Planned | RCRC GIS escalation for missing layers
9 | Hold RCRC internal Stage 4 gate | WSP PM | 2026-07-14 | RCRC | Confirm readiness for external meetings | Decision and escalation log | Planned | Move decision to PM forum if not held
10 | Issue meeting requests for first wave external meetings | Stakeholder Lead / Lubna | 2026-07-20 | MoE, Amanah, MEWA, Royal Reserve | Secure calendar slots | Scheduled meetings | Planned | RCRC to send formal requests

## 10_Info Required (hidden)
Information Required Register
This register clearly separates missing/uncertain information from confirmed inputs.
Info ID | Information Required | Required From | Why Needed for Stage 4 | Linked Deliverable | Priority | Target Date | Status | Notes / Assumption
IR-01 | Final Stage 4 milestone dates and internal approval gates | RCRC / WSP PM | To finalize stakeholder schedule | Engagement Schedule | Critical | 2026-07-14 | Information Required | Current dates are proposed assumptions
IR-02 | Confirmed stakeholder focal points and decision-makers | RCRC / Lubna | To avoid meetings without authority | All stakeholder meetings | Critical | 2026-07-16 | Information Required | Needed before invitations
IR-03 | Stage 3 preferred strategy / structure plan outputs approved internally | RCRC / WSP | Required before sharing with external stakeholders | Structure Plan | Critical | 2026-07-20 | Information Required | MoE requested outputs once approved
IR-04 | HEC-HMS and HEC-RAS files | Riyadh Municipality | Supports 2D hydrology model and flood buffers | 2D Hydrology Model | Critical | 2026-07-22 | Open - verify status | Promised where available
IR-05 | Hydrology reports/drawings for important wadis | Riyadh Municipality / Wadi Al-Sulai | Supports wadi boundaries and buffers | Structure Plan / EIA | Critical | 2026-07-22 | Open - verify status | Old data must be validated
IR-06 | Culvert, stormwater asset and spot level data | Riyadh Municipality | Supports drainage network and flood modelling | 2D Hydrology Model | High | 2026-07-22 | Open - verify status | Coordinate system metadata required
IR-07 | Pipeline-affected land GIS and buffer zones | MoE / Aramco / RCRC | Impacts developable land and parcel treatment | Structure Plan | Critical | 2026-07-20 | Open - verify status | Include title deed status if available
IR-08 | Permission to share Royal Orders No. 40023 and 34738 or summary note | RCRC Legal | Supports MoE alignment on pipeline-affected lands | Legal / Stakeholder Alignment | High | 2026-07-20 | Information Required | Internal verification required
IR-09 | Power demand assumptions and substation requirements | RCRC / SEC / National Grid | Required for power network and cost estimates | Infrastructure / Cost | Critical | 2026-07-27 | Information Required | NEC stated demand not confirmed
IR-10 | Committee No.85 representatives to include in meetings | RCRC | Avoid duplication of pipeline coordination | Engagement Schedule | High | 2026-07-20 | Information Required | Names identified in MoE MoM
IR-11 | Plot No.2 status and housing-sector plans | MOMAH / RCRC | Affects land use and ownership treatment | Structure Plan | High | 2026-07-30 | Open - verify status | Subject to confirmation
IR-12 | Confirmed future plans within project boundary | MOMAH | Affects land use and development direction | Master Plan | High | 2026-07-30 | Open - verify status | Requested by RCRC
IR-13 | MIMR mineral/silica/sand reserve boundaries and restrictions | MIMR | Affects land suitability and no-go zones | Structure Plan | Critical | 2026-08-05 | Information Required | Priority from recent client request
IR-14 | MEWA environmental and water constraints | MEWA / SIO | Supports EIA, water/wadi constraints and mitigation | EIA / Structure Plan | High | 2026-07-26 | Information Required | Focal point required
IR-15 | Royal Reserve ecological corridor comments and data | Royal Reserve Authority | Supports reserve interface and environmental framework | EIA / Structure Plan | High | 2026-07-28 | Open - verify status | Previous queries via Excel
IR-16 | RIPC 5-year strategy and service provider coverage | RIPC | Supports infrastructure phasing and funding | Infrastructure Plan | High | 2026-08-03 | Open - verify status | Subject to approvals
IR-17 | SPGA ownership dataset | SPGA | Supports land consolidation and parcel treatment | Land Consolidation | Critical | 2026-08-11 | Open - verify status | No confirmed status in provided notes
IR-18 | MOJ title deed and legal status data | Ministry of Justice | Validates ownership methodology and legal treatment | Land / Legal | Critical | 2026-08-11 | Open - verify status | No confirmed status in provided notes
IR-19 | MOD/MOI restricted land boundaries | RCRC / relevant ministries | No development or relocation into MOD/MOI lands | Constraints Map | Critical | 2026-07-24 | Information Required | Need latest GIS
IR-20 | Stakeholder response status for all previous MoM actions | RCRC / WSP Leads | To close action tracker before Stage 4 issue | Previous Meetings Tracker | High | 2026-07-24 | Information Required | Many prior actions lack documented closure

## 11_Source Notes (hidden)
Source Notes and Assumptions
The workbook is grounded in the supplied Stage 2/3 MoMs, SEMP and Stage 3 workshop materials. Any missing information is flagged in the Information Required register.
Source | Date | Used For | Key Extracted Points
SEMP - Stakeholder Engagement Plan and Management | 18-Dec-2025 | Framework, stakeholder categories, engagement methods, risk approach | Stage 4 includes structure plan and master plan update presentations/workshops; stakeholders mapped by role, influence and interest
Riyadh Plan Alignment MoM | 17-Feb-2026 | Strategic direction and Stage 3 to Stage 4 assumptions | Visioning to focus on mission/role/principles; no-go zones, hydrology and plot-for-plot principles
Royal Reserve Authority MoM | 04-May-2026 | Reserve interface and environmental follow-up | Ecological corridors, watersheds, environmental integration and spatial data contradictions
Ministry of Energy MoM | 11-May-2026 | Energy constraints and meeting protocol | Arabic meetings, presentation+Excel queries, pipeline/power constraints and demand requirements
RIPC MoM | 12-May-2026 | Infrastructure phasing and funding | KMZ verification, 5-year vision, service provider strategies, funding mechanism
MOMAH MoM | 14-May-2026 | Planning/housing alignment | Land ownership, building status, compensation, approved plans, Plot No.2
Wadi Al-Sulai MoM | 18-May-2026 | Wadi protection and buffer approach | Dynamic buffers; protection takes priority; hydrology and vegetation studies required
Riyadh Municipality Stormwater MoM | 18-Jun-2026 | Hydrology data and model requirements | Old hydrology study is not reliable; HEC-HMS/RAS, culvert and survey data requested
MoE Second Coordination MoM | 07-Jul-2026 | MoE Stage 4 follow-up and dry utility cost process | MoE as strategic partner; meetings every 3 weeks; Committee No.85; share Stage 3 outputs once approved
Stage 3 VP/Steering Committee deck | Jun-2026 | Stage 4 deliverables and programme context | Stage 4 includes structural plan report, master plan report, EIA report and 2D hydrological model
Assumption ID | Assumption
A-01 | Proposed dates start from 14-Jul-2026 and should be confirmed by RCRC/Lubna.
A-02 | Where MoM actions had blank owner/due dates, the workbook marks them as Information Required / Open - verify status instead of assigning unconfirmed responsibility.
A-03 | Meetings are structured for Stage 4 validation and action closure, not baseline data collection only.
A-04 | RCRC remains the central coordinator and decision route for conflicting stakeholder positions.

## 07_Data Requests (hidden)
Entity / Stakeholder Name | Requested Data | Status: Received / Not Received / To be filled manually
Amanah / Riyadh Municipality | Complete granted plots dataset for all 51k+ parcels, including the 6,128 missing/unidentified granted parcels with parcel numbers, locations, and grantee names. | Received
Ministry of Justice (MOJ) | Title deed status / ownership verification for the remaining 13,851 parcels under review. | Received
Ministry of Justice (MOJ) | Ownership records / title deed verification for compensation plans 3137, 3138, 3140, 3141; government plan 3210; utilities plan 3143; and informal development outside the Development Protection Boundary south of the project area. | Received
State Properties General Authority (SPGA / GASP) | Official responses/data on governmental land classification, legal status, ownership transfer to GASP, allocation type, responsible entities, development programs, and expected timelines. | Received
State Properties General Authority (SPGA / GASP) | Official clarification on governmental lands outside the Development Protection Boundary, including allocation decisions, official directives, and whether land replacement is required where development is constrained. | Received
Ministry of Industry and Mineral Resources (MIM) | Clarification/data on future industrial activities, development vision, employment requirements, and staff accommodation related to the silica / industrial overlap area. | To be filled manually
Imam Abdulaziz bin Muhammad Royal Reserve Authority | Responses to project queries, comments, and requirements via the structured Excel tracker. | To be filled manually
Imam Abdulaziz bin Muhammad Royal Reserve Authority | Hydrology, environmental, and ecological integration inputs, including ecological corridors, watershed implications, and interface with the Royal Reserve. | To be filled manually
MEWA | Strategic coordination model/template for review by RCRC and WSP. | To be filled manually
MEWA | Environmental assessment model/template for review by RCRC and WSP. | To be filled manually
Riyadh Municipality - General Directorate of Stormwater Networks | Updated survey data and hydrological data, including recent studies, models, and GIS layers if available. | To be filled manually
Riyadh Municipality - General Directorate of Stormwater Networks | Available HEC-HMS and HEC-RAS model files related to the previous Amanah hydrological study. | To be filled manually
Riyadh Municipality - General Directorate of Stormwater Networks | Reports, drawings, and data related to important wadis within or near the project area. | To be filled manually
Riyadh Municipality - General Directorate of Stormwater Networks | Information on existing culverts and stormwater infrastructure, including built stormwater assets, channels, flood management structures, and flood-affected areas. | To be filled manually
Riyadh Municipality - General Directorate of Stormwater Networks | Spot levels and survey information related to hydrology infrastructure, including coordinate system details and data accuracy/relevance. | To be filled manually
Riyadh Plan Team | Riyadh Plan alignment inputs, including polycentric city structure, population and employment distribution logic, hierarchy of centres, transport networks, and unit rates. | To be filled manually
Ministry of Energy / Saudi Aramco | Pipeline alignment, protection zones, required setbacks, and permitted/restricted land uses for the Saudi Aramco corridor. | To be filled manually
Ministry of Energy / SEC / National Grid | Future electricity demand forecasts, load requirements, substation planning inputs, and grid reinforcement plans. | To be filled manually
Ministry of Energy / SEC / National Grid | Clarification on feasibility and constraints for undergrounding or rerouting high-voltage overhead transmission lines. | To be filled manually
Ministry of Municipalities and Housing (MOMAH) | Confirmation on Plot No. 2 ownership / housing-sector relationship and any Ministry future plans within the project boundary. | To be filled manually
Ministry of Municipalities and Housing (MOMAH) | Feedback on shared project materials and clarifications on land ownership, building licensing status, post-Royal Decree development status, compensation approach, and future land-use alignment. | To be filled manually
Riyadh Municipality - Land and Property Departments | Inputs on affected lands and compensation mechanisms related to wadi intersections and Wadi Al-Sulai coordination. | To be filled manually
Wadi Al-Sulai Project Team | Available environmental and vegetation studies relevant to Project East Grant and wadi protection planning. | To be filled manually
Wadi Al-Sulai Project Team | Wadi buffer approach, classification methodology, and relevant hydrology/environmental inputs for assessing applicability to Project East Grant. | To be filled manually